## Partner Opp Referral - Create
Step # |  | Step by Step Instructions | Expected Results | Pass/Fail | User Notes
Partner Opp Referral Test cases
Business process : Partner creates an opportunity through the UI on Partner Central (or Bulk Import process) [Partner Referral identified by opportunityOwnership ="Partner Referral"]
1 | Create with Mandatory Fields | Fill in the following details for these 14 mandatory fields along with a new partnerCrmUniqueIdentifier { "version": "1", "spmsId": "XXXXX", "opportunities": [ { "useCase": "Business Applications", "targetCloseDate": "2020-06-30", "projectDescription": "Automation Platform development for bank. Need support in understanding customer requirements and any background on their cloud projects", "postalCode": "84133", "partnerProjectTitle": "AllySegall - Development Platform", "partnerPrimaryNeedFromAws": "Architectural validation", "partnerCrmUniqueIdentifier": "PR123456", "industry": "Financial Services", "expectedMonthlyAwsRevenue": 100.0, "deliveryModel": "SaaS or PaaS", "customerWebsite": "ally.com", "customerCompanyName": "Ally Segall", "country": "United States", "state": "Alaska" } ] } | New opportunity created and a successful response "inboundApiResults": [ { "partnerCrmUniqueIdentifier": "PR123456", "isSuccess": true, "errors": null, "apnCrmUniqueIdentifier": "O191831" } | Pass
2 | Create with Mandatory Fields and Partner Sales Contact Information | Fill in the following details for these 14 mandatory fields along with a new partnerCrmUniqueIdentifier and the partner sales contact information { "version": "1", "spmsId": "88888", "opportunities": [ { "useCase": "Business Applications", "targetCloseDate": "2020-06-30", "projectDescription": "Automation Platform development for bank. Need support in understanding customer requirements and any background on their cloud projects", "postalCode": "84133", "partnerProjectTitle": "AllySegall - Development Platform", "partnerPrimaryNeedFromAws": "Architectural validation", "partnerCrmUniqueIdentifier": "PR1234567", "industry": "Financial Services", "expectedMonthlyAwsRevenue": 100.0, "deliveryModel": "SaaS or PaaS", "customerWebsite": "ally.com", "customerCompanyName": "Ally Segall", "country": "United States", "state": "Alaska" , "primaryContactPhone": "5555555", "primaryContactLastName": "PartnerSalesRepLastName", "primaryContactFirstName": "PartnerSalesRepFirstName", "primaryContactEmail": "PartnerSalesRepLastName@partner.com" } ] } | New opportunity created and a successful response "inboundApiResults": [ { "partnerCrmUniqueIdentifier": "PR1234567", "isSuccess": true, "errors": null, "apnCrmUniqueIdentifier": "O191832" } ], | Pass
3 | Create with Mandatory Fields and Partner Sales Contact Information and Customer Contact details | Fill in the following details for these 14 mandatory fields along with a new partnerCrmUniqueIdentifier and the partner sales contact information and the customer contact details { "version": "1", "spmsId": "88888", "opportunities": [ { "useCase": "Business Applications", "targetCloseDate": "2020-06-30", "projectDescription": "Automation Platform development for bank. Need support in understanding customer requirements and any background on their cloud projects", "postalCode": "84133", "partnerProjectTitle": "AllySegall - Development Platform", "partnerPrimaryNeedFromAws": "Architectural validation", "partnerCrmUniqueIdentifier": "PR12345678", "industry": "Financial Services", "expectedMonthlyAwsRevenue": 100.0, "deliveryModel": "SaaS or PaaS", "customerWebsite": "ally.com", "customerCompanyName": "Ally Segall", "country": "United States", "state": "Alaska" , "primaryContactPhone": "5555555", "primaryContactLastName": "PartnerSalesRepLastName", "primaryContactFirstName": "PartnerSalesRepFirstName", "primaryContactEmail": "PartnerSalesRepLastName@partner.com", "customerTitle": "mr", "customerPhone": "99999999", "customerLastName": "customerlastname", "customerFirstName": "customerfirstname", "customerEmail": "cust@cust.com" } ] } | New opportunity created and a successful response "inboundApiResults": [ { "partnerCrmUniqueIdentifier": "PR12345678", "isSuccess": true, "errors": null, "apnCrmUniqueIdentifier": "O191833" } ], | Pass
4 | Create with all possible fields | Fill in the following details for these 14 mandatory fields along with a new partnerCrmUniqueIdentifier and the partner sales contact information and the customer contact details and all other optional information in the JSON { "version": "1", "spmsId": "88888", "opportunities": [ { "useCase": "Business Applications", "targetCloseDate": "2020-06-30", "projectDescription": "Automation Platform development for bank. Need support in understanding customer requirements and any background on their cloud projects", "postalCode": "84133", "partnerProjectTitle": "AllySegall - Development Platform", "partnerPrimaryNeedFromAws": "Architectural validation", "partnerCrmUniqueIdentifier": "PR123456789", "industry": "Financial Services", "expectedMonthlyAwsRevenue": 100.0, "deliveryModel": "SaaS or PaaS", "customerWebsite": "ally.com", "customerCompanyName": "Ally Segall", "country": "United States", "state": "Alaska" , "primaryContactPhone": "5555555", "primaryContactLastName": "PartnerSalesRepLastName", "primaryContactFirstName": "PartnerSalesRepFirstName", "primaryContactEmail": "PartnerSalesRepLastName@partner.com", "customerTitle": "mr", "customerPhone": "99999999", "customerLastName": "customerlastname", "customerFirstName": "customerfirstname", "customerEmail": "cust@cust.com" , "wWPSPDMEmail": "WWPS@AMAZON.COM", "wWPSPDM": "WWPS", "subUseCase": "SAP Production", "streetAddress": "123asasa", "status": "Approved", "stage": "Launched", "publicReferenceUrl": "HTTPS://URL.COM", "publicReferenceTitle": "prt", "partnerPrimaryNeedFromAwsOther": "other", "partnerDeveloperManagerPhone": "123", "partnerDeveloperManagerEmail": "pdm@amaz.com", "partnerDeveloperManager": "pdm", "partnerAcceptanceStatus": "Rejected", "opportunityOwnership": "PReferral", "opportunityOwnerName": "Gabriela Cohen", "opportunityOwnerEmail": "partner-systems+aws-partner-net@amazon.com.invalid", "nextStepHistory": "nxt", "nextStep": "nxt", "leadSource": "lsource", "lastModifiedDate": null, "lastModifiedBy": null, "isThisForMarketplace": "No", "isThisAPublicReference": "No", "isNetNewBusinessForCompany": "No", "isMarketingDevelopmentFunded": "No", "industryOther": "other", "createdDate": null, "createdBy": null, "contractVehicle": null, "competitiveTrackingOther": "other", "competitiveTracking": "Oracle Cloud", "closedLostReason": null, "city": "city", "campaignName": "c123", "aWSStage": "Launched", "aWSSalesRepName": "awsrep", "aWSSalesRepEmail": "awsrep@amazon.com", "aWSPartnerSuccessManagerName": "psm", "aWSPartnerSuccessManagerEmail": "psm@amazon.com", "aWSISVSuccessManagerName": "isvsuccessname", "aWSISVSuccessManagerEmail": "isv@amazon.com", "awsFieldEngagement": "No", "aWSCloseDate": null, "aWSAccountOwnerName": "am", "aWSAccountOwnerEmail": "am@amazon.com", "awsAccountId": "123456789123", "additionalComments": "Acomments", "apnCrmUniqueIdentifier": null } ] } | New opportunity created and a successful response "inboundApiResults": [ { "partnerCrmUniqueIdentifier": "PR123456789", "isSuccess": true, "errors": null, "apnCrmUniqueIdentifier": "O191834" } ], The following fields are not considered during create and are ignored as they are not expected from Partners during creation and are readonly "wWPSPDMEmail": "WWPS@AMAZON.COM", "wWPSPDM": "WWPS", "status": "Approved", "stage": "Launched", "opportunityOwnership": "PReferral", "nextStepHistory": "nxt", "nextStep": "nxt", "leadSource": "lsource", "lastModifiedDate": null, "lastModifiedBy": null, "isNetNewBusinessForCompany": "No", "createdDate": null, "createdBy": null, "closedLostReason": null, "aWSStage": "Launched", "aWSSalesRepName": "awsrep", "aWSSalesRepEmail": "awsrep@amazon.com", "aWSPartnerSuccessManagerName": "psm", "aWSPartnerSuccessManagerEmail": "psm@amazon.com", "aWSISVSuccessManagerName": "isvsuccessname", "aWSISVSuccessManagerEmail": "isv@amazon.com", "aWSCloseDate": null, "aWSAccountOwnerName": "am", "aWSAccountOwnerEmail": "am@amazon.com", "apnCrmUniqueIdentifier": null | Pass
5 | Error while creating with the same PartnercrmUniqueIdentifier | Try creating a new Opportunity with an already existing PartnerCRMidentifier in the ACE system (In this example we used PR1234567 as an opportunity already exists in ACE for the same partner with the same id { "version": "1", "spmsId": "88888", "opportunities": [ { "useCase": "Business Applications", "targetCloseDate": "2020-06-30", "projectDescription": "Automation Platform development for bank. Need support in understanding customer requirements and any background on their cloud projects", "postalCode": "84133", "partnerProjectTitle": "AllySegall - Development Platform", "partnerPrimaryNeedFromAws": "Architectural validation", "partnerCrmUniqueIdentifier": "PR1234567", "industry": "Financial Services", "expectedMonthlyAwsRevenue": 100.0, "deliveryModel": "SaaS or PaaS", "customerWebsite": "ally.com", "customerCompanyName": "Ally Segall", "country": "United States", "state": "Alaska" , "primaryContactPhone": "5555555", "primaryContactLastName": "PartnerSalesRepLastName", "primaryContactFirstName": "PartnerSalesRepFirstName", "primaryContactEmail": "PartnerSalesRepLastName@partner.com", "customerTitle": "mr", "customerPhone": "99999999", "customerLastName": "customerlastname", "customerFirstName": "customerfirstname", "customerEmail": "cust@cust.com" } ] } | This does not create a new opportunity and either updates or provides an error message that the record is not editable (if being reviewed by AWS) "inboundApiResults": [ { "partnerCrmUniqueIdentifier": "PR1234567", "isSuccess": false, "errors": [ "Record is not editable." ], "apnCrmUniqueIdentifier": null } ], | Pass
Business process : Validations during Create [Partner Referral identified by opportunityOwnership ="Partner Referral"]
6.1 | Create Validations | The following fields are mandatory on the opportunity (If any of these fields are missing then the opportunity will not be created) "useCase": "Business Applications", "targetCloseDate": "2020-06-30", "projectDescription": "Automation Platform development for bank. Need support in understanding customer requirements and any background on their cloud projects", "postalCode": "84133", "partnerProjectTitle": "AllySegall - Development Platform", "partnerPrimaryNeedFromAws": "Architectural validation", "partnerCrmUniqueIdentifier": "PR123456", "industry": "Financial Services", "expectedMonthlyAwsRevenue": 100.0, "deliveryModel": "SaaS or PaaS", "customerWebsite": "ally.com", "customerCompanyName": "Ally Segall", "country": "United States", "state": "Alaska" | Partners will get an error if the update does not adhere to this validation { "partnerCrmUniqueIdentifier": "PR123456789101", "isSuccess": false, "errors": [ "Required: Use Case;Target Launch Date;Project Description/Business Need;Postal Code;Partner Project Title;Industry Vertical;Expected Monthly AWS Revenue;Expected Monthly AWS Revenue;Delivery Model;Customer Website;Customer Company Name;Country;Partner Primary Need from AWS" ], "apnCrmUniqueIdentifier": null } ], | Pass
6.2 | Create Validations | For Public Sector partner where Industry = (Education or Government) and Country = United States contractvehicle is mandatory | Partners will get an error if the update does not adhere to this validation | Pass
6.3 | Create Validations | The following field updates take in only standard values partnerPrimaryNeedFromAws competitiveTracking useCase subUseCase isThisForMarketplace isMarketingDevelopmentFunded deliveryModel awsFieldEngagement industry | Partners will get an error if the update does not adhere to this validation | Pass
6.4 | Create Validations | If Country is "United States", State is a required field | Partners will get an error if the update does not adhere to this validation | Pass
6.5 | Create Validations | AWS Account ID needs to be a 12 digit numbers | Partners will get an error if the update does not adhere to this validation | Pass
6.6 | Create Validations | expectedMonthlyAwsRevenue cannot be negaitive or Zero | Partners will get an error if the update does not adhere to this validation | Pass
6.7 | Create Validations | partnerCrmUniqueIdentifier is unique and a new entry for create opportunity | Partners will get an error if the update does not adhere to this validation | Pass

## Partner Opp Referral
Step # |  | Step by Step Instructions | Expected Results | Pass/Fail | User Notes
Partner Opp Referral Test cases
Business process : Partner creates an opportunity through the UI on Partner Central (or Bulk Import process) [Partner Referral identified by opportunityOwnership ="Partner Referral"]
1 | Partner imports new opportunities successfully through the integration | Refer Test scripts on sheet "Partner Opp Referral - Create"
Business process : AWS accepts or rejects a partner submission based on information shared [[Partner Referral identified by opportunityOwnership ="Partner Referral"]
2 | AWS Approves the Opportunity | Read the latest file from the Opportunity-outbound folder. | The opportunity-outbound folder will have the latest file with Status = Approved On Approval, partner is able to view additional information from AWS such as the AWS Sales Rep details. Partner can ingest this information back into their CRM | Pass
2.1 | AWS Rejects Opportunity (Alternate option) | Read the latest file from the Opportunity-outbound folder. | The opportunity-outbound folder will have the latest file with Status = Rejected On Rejection, partner is not able to view additional information from AWS such as the AWS Sales Rep details. Partner can ingest this information back into their CRM | Pass
2.2 | AWS is reviewing the opportunity | Read the latest file from the Opportunity-outbound folder. | The opportunity-outbound folder will have the latest file with Status = In review On Rejection, partner is not able to view additional information from AWS such as the AWS Sales Rep details. Partner can ingest this information back into their CRM | Pass
Business process : Partner is able to update approved opportunities [Partner Referral identified by opportunityOwnership ="Partner Referral"]
3 | Updatable Fields | As a Partner user I should be able to update the following fields by placing a file in a JSON format in the opportunity-inbound folder. I can send 1 or many of these fields along with the unique identifiers - apnCrmUniqueIdentifier and/or partnerCrmUniqueIdentifier Important pipeline fields highlighted in red { "version" : "1", "spmsId" : "397476", "opportunities" : [ { "useCase" : "AI/Machine Learning", "targetCloseDate" : "2020-05-30", "subUseCase" : "Language Translation", "streetAddress" : "1015E/A,SS~!@#$%^&&**(()((<><>??''", "stage" : "XYZ", "expectedMonthlyAwsRevenue" : 3567.0, "deliveryModel" : "SaaS or PaaS", "primaryContactPhone" : "HC1", "primaryContactLastName" : "HC2", "primaryContactFirstName" : "HC3", "primaryContactEmail" : "HC@HC.VOM", "partnerPrimaryNeedFromAws" : "Architectural validation", "partnerPrimaryNeedFromAwsOther" : "oTHER", "partnerCrmUniqueIdentifier" : "hc1234", "nextStep" : "02/08/2020: Contact Aldo 55", "isThisAPublicReference" : "No2", "publicReferenceUrl" : "Yes", "publicReferenceTitle" : "Title3", "isThisForMarketplace" : "No", "isNetNewBusinessForCompany" : "Yes", "isMarketingDevelopmentFunded" : "Yes", "industry" : "Business Serv. 2", "industryOther" : "Other", "customerTitle" : "Sr. Director2, Alliances", "customerPhone" : "+1 925-818-34342", "customerLastName" : "Doss2", "customerFirstName" : "Al2", "customerEmail" : "aws_alliance2@hashicorp.com.apnuatnew", "contractVehicle" : "1223", "competitiveTracking" : "Oracle Cloud", "competitiveTrackingOther" : "Other", "closedLostReason" : "Closed", "city" : "Bangalore", "campaignName" : "Prospecting days", "awsFieldEngagement" : "Yes", "awsAccountId" : "123456789112", "apnCrmUniqueIdentifier" : "O253273", "additionalComments" : "Check" }]} | The opportunity-inbound-processed-results folder will have the same file name as the input along with results appended to the end of the file name. The results file will highlight successful updates or errors if any. Internally within AWS, the AWS seller is able to view the partner updates on the opportunity Note: If fields which are not updatable are shared, they will be ignored in the updates | Pass
3.1 | Update Validations | For an ISV Accelerate program partner isNetNewBusinessForCompany is mandatory before Stage = Launched awsFieldEngagement is mandatory before Stage = Launched | Partners will get an error if the update does not adhere to this validation | Pass
3.2 | Update Validations | The following fields are mandatory on the opportunity (Note: if already available on the APN opportunity you are not required to share it subsequently) useCase targetCloseDate stage partnerPrimaryNeedFromAws expectedMonthlyAwsRevenue deliveryModel | Partners will get an error if the update does not adhere to this validation | Pass
3.3 | Update Validations | For consulting partners Stage cannot be updated to Launched till AWSAccountID (12 digit number) is updated | Partners will get an error if the update does not adhere to this validation | Pass
3.4 | Update Validations | For Public Sector partner where Industry = (Education or Government) and Country = United States contractvehicle is mandatory | Partners will get an error if the update does not adhere to this validation | Pass
3.5 | Update Validations | AWSclosedlost reason is mandatory if Stage = Closed Lost | Partners will get an error if the update does not adhere to this validation | Pass
3.6 | Update Validations | The following fields can be updated only when Stage = Launched isThisAPublicReference publicReferenceUrl publicReferenceTitle | Partners will get an error if the update does not adhere to this validation | Pass
3.7 | Update Validations | The following field updates take in only standard values partnerPrimaryNeedFromAws competitiveTracking useCase subUseCase partnerAcceptanceStatus stage isThisForMarketplace isThisAPublicReference isNetNewBusinessForCompany isMarketingDevelopmentFunded deliveryModel awsFieldEngagement Closed Lost reason | Partners will get an error if the update does not adhere to this validation | Pass
3.8 | Update Validations | Partner is not able to update opportunities where Status not equal to Approved | Partners will get an error if the update does not adhere to this validation | Pass
3.9 | Update Validations | Partner is not able to update pipeline fields on the opportunity where Stage = Launched | Partners will get an error if the update does not adhere to this validation | Pass
Business process : Partner is able to consume updates from AWS Seller such as next steps, stage, close date [Partner Referral identified by opportunityOwnership ="Partner Referral"]
4 | Next Steps | As a partner user I should check visibility of the next steps, stage, targetCloseDate, expectedMonthlyAwsRevenue provided by AWS seller. Read the latest file from the Opportunity-outbound folder. | As a partner user I should be able to view the next steps shared by AWS. Partner is able to ingest this information into their CRM against the same record into their CRM | Pass

## AWS Opp Referral
Step # |  | Step by Step Instructions | Expected Results | Pass/Fail | User Notes
AWS Opp Referral Test cases
Business process : AWS Sales rep shares an opportunity with the Partner (AWS Referral identified by OpportunityOwnership = "AWS Referral")
1 | PII information (prior to accepting opportunity) | Read the latest file from the Opportunity-outbound folder. (Opportunity Ownership = "AWS Referral") | As a partner user I should be able to view a new opportunity shared by AWS includes details such as company name and project title but not able to view PII information such as customer first name, last name, email, phone (prior to acceptance). Partner is able to ingest this information into their CRM and allocate to the right individual | Pass
Business process : Partner Accepts or Rejects the AWS referral opportunity (AWS Referral identified by OpportunityOwnership = "AWS Referral")
2 | Accept Opportunity | As a partner user I should be able to "Accept" an opportunity by placing a file in the opportunity-inbound folder with the below format { "version" : "1", "spmsId" : "397476", "opportunities" : [ { "partnerAcceptanceStatus" : "Accepted", "apnCrmUniqueIdentifier" : "OXXXXXX" } ] } | The opportunity-inbound-processed-results folder will have the same file name as the input along with results appended to the end of the filer name. The results file will highlight successful acceptance Further On Acceptance, partner is able to view PII information on the opportunity on subsequent reads from the opportunity-outbound folder. Internally within AWS, the AWS is able to view the partner acceptance on the opportunity | Pass
2.1 | Reject Opportunity (Alternate option) | As a partner user I should be able to "Accept" an opportunity by placing a file in the opportunity-inbound folder with the below format { "version" : "1", "spmsId" : "397476", "opportunities" : [ { "partnerAcceptanceStatus" : "Rejected", "apnCrmUniqueIdentifier" : "OXXXXXX" } ] } | The opportunity-inbound-processed-results folder will have the same file name as the input along with results appended to the end of the file name. The results file will highlight successful rejection Further On rejection, partner is not able to view PII information on the opportunity on subsequent reads from the opportunity-outbound folder. Internally within AWS, the AWS seller is able to view the partner rejection on the opportunity | Pass
Business process : Partner is able to read PII information of accepted opportunities (AWS Referral identified by OpportunityOwnership = "AWS Referral")
3 | PII information (post accepting opportunity) | Read the latest file from the Opportunity-outbound folder. | As a partner user I should be able to view the accepted opportunity shared by AWS including PII information such as customer first name, last name, email, phone. Partner is able to ingest this information into their CRM against the same record into their CRM | Pass
Business process : Partner is able to update an accepted opportunity (AWS Referral identified by OpportunityOwnership = "AWS Referral")
4 | Updatable Fields | As a Partner user I should be able to update the following fields by placing a file in a JSON format in the opportunity-inbound folder. I can send 1 or many of these fields along with the unique identifiers - apnCrmUniqueIdentifier and/or partnerCrmUniqueIdentifier Important pipeline fields highlighted in red { "version" : "1", "spmsId" : "397476", "opportunities" : [ { "useCase" : "AI/Machine Learning", "targetCloseDate" : "2020-05-30", "subUseCase" : "Language Translation", "streetAddress" : "1015E/A,SS~!@#$%^&&**(()((<><>??''", "stage" : "XYZ", "expectedMonthlyAwsRevenue" : 3567.0, "deliveryModel" : "SaaS or PaaS", "primaryContactPhone" : "HC1", "primaryContactLastName" : "HC2", "primaryContactFirstName" : "HC3", "primaryContactEmail" : "HC@HC.VOM", "partnerPrimaryNeedFromAws" : "Architectural validation", "partnerPrimaryNeedFromAwsOther" : "oTHER", "partnerCrmUniqueIdentifier" : "hc1234", "nextStep" : "02/08/2020: Contact Aldo 55", "isThisAPublicReference" : "No2", "publicReferenceUrl" : "Yes", "publicReferenceTitle" : "Title3", "isThisForMarketplace" : "No", "isNetNewBusinessForCompany" : "Yes", "isMarketingDevelopmentFunded" : "Yes", "industry" : "Business Serv. 2", "industryOther" : "Other", "customerTitle" : "Sr. Director2, Alliances", "customerPhone" : "+1 925-818-34342", "customerLastName" : "Doss2", "customerFirstName" : "Al2", "customerEmail" : "aws_alliance2@hashicorp.com.apnuatnew", "contractVehicle" : "1223", "competitiveTracking" : "Oracle Cloud", "competitiveTrackingOther" : "Other", "closedLostReason" : "Closed", "city" : "Bangalore", "campaignName" : "Prospecting days", "awsFieldEngagement" : "Yes", "awsAccountId" : "123456789112", "apnCrmUniqueIdentifier" : "O253273", "additionalComments" : "Check" }]} | The opportunity-inbound-processed-results folder will have the same file name as the input along with results appended to the end of the file name. The results file will highlight successful updates or errors if any. Internally within AWS, the AWS seller is able to view the partner updates on the opportunity Note: If fields which are not updatable are shared, they will be ignored in the updates | Pass
4.1 | Update Validations | For an ISV Accelerate program partner isNetNewBusinessForCompany is mandatory before Stage = Launched awsFieldEngagement is mandatory before Stage = Launched | Partners will get an error if the update does not adhere to this validation | Pass
4.2 | Update Validations | The following fields are mandatory on the opportunity (Note: if already available on the APN opportunity you are not required to share it subsequently) useCase targetCloseDate stage partnerPrimaryNeedFromAws expectedMonthlyAwsRevenue deliveryModel | Partners will get an error if the update does not adhere to this validation | Pass
4.3 | Update Validations | For consulting partners Stage cannot be updated to Launched till AWSAccountID (12 digit number) is updated | Partners will get an error if the update does not adhere to this validation | Pass
4.4 | Update Validations | For Public Sector partner where Industry = (Education or Government) and Country = United States contractvehicle is mandatory | Partners will get an error if the update does not adhere to this validation | Pass
4.5 | Update Validations | AWSclosedlost reason is mandatory if Stage = Closed Lost | Partners will get an error if the update does not adhere to this validation | Pass
4.6 | Update Validations | The following fields can be updated only when Stage = Launched isThisAPublicReference publicReferenceUrl publicReferenceTitle | Partners will get an error if the update does not adhere to this validation | Pass
4.7 | Update Validations | The following field updates take in only standard values partnerPrimaryNeedFromAws competitiveTracking useCase subUseCase partnerAcceptanceStatus stage isThisForMarketplace isThisAPublicReference isNetNewBusinessForCompany isMarketingDevelopmentFunded deliveryModel awsFieldEngagement Closed Lost reason | Partners will get an error if the update does not adhere to this validation | Pass
4.8 | Update Validations | Partner is not able to update opportunities where Partner Acceptance Status not equal to Accepted | Partners will get an error if the update does not adhere to this validation | Pass
4.9 | Update Validations | Partner is not able to update pipeline fields on the opportunity where Stage = Launched | Partners will get an error if the update does not adhere to this validation | Pass
Business process : Partner is able to consume updates from AWS Seller such as next steps (AWS Referral identified by OpportunityOwnership = "AWS Referral")
5 | Next Steps | As a partner user I should check visibility of the next steps provided by AWS seller. Read the latest file from the Opportunity-outbound folder. | As a partner user I should be able to view the next steps shared by AWS. Partner is able to ingest this information into their CRM against the same record into their CRM | Pass

## AWS Lead Referral
Step # |  | Step by Step Instructions | Expected Results | Pass/Fail | User Notes
AWS Lead Referral Test cases
Business process : AWS Sales rep shares a lead with the Partner
1 | PII information (prior to accepting lead) | Read the latest file from the lead-inbound folder. | As a partner user I should be able to view a new lead shared by AWS includes details such as company size, Industry and project title but not able to view PII information such as customer first name, last name, email, phone (prior to acceptance). Partner is able to ingest this information into their CRM and allocate to the right individual | Pass | Reactive: Current lead stage is not in the outbound JSON
Business process : Partner Accepts or Rejects the AWS referral opportunity (AWS Referral identified by OpportunityOwnership = "AWS Referral")
2 | Accept Lead | As a partner user I should be able to "Accept" an opportunity by placing a file in the opportunity-inbound folder with the below format { "version": "1", "spmsId": "397476", "leads": [ { "current lead stage": "Accepted", "apnCrmUniqueIdentifier": "L128676" } ] } | The lead-inbound-processed-results folder will have the same file name as the input along with results appended to the end of the filer name. The results file will highlight successful acceptance Further On Acceptance, partner is able to view PII information on the lead on subsequent reads from the lead-outbound folder. | Fail | Tracked as a follow up: current lead stage is not being accepted in the inbound JSON
2.1 | Reject Lead(Alternate option) | As a partner user I should be able to "Accept" an opportunity by placing a file in the opportunity-inbound folder with the below format { "version": "1", "spmsId": "397476", "leads": [ { "current lead stage": "Rejected", "apnCrmUniqueIdentifier": "L128676" } ] } | The lead-inbound-processed-results folder will have the same file name as the input along with results appended to the end of the file name. The results file will highlight successful rejection Further On rejection, partner is not able to view PII information on the opportunity on subsequent reads from the opportunity-inbound folder. | Fail | Tracked as a follow up: current lead stage is not being accepted in the inbound JSON
Business process : Partner is able to read PII information of accepted opportunities (AWS Referral identified by OpportunityOwnership = "AWS Referral")
3 | PII information (post accepting opportunity) | Read the latest file from the Opportunity-outbound folder. | As a partner user I should be able to view the accepted lead shared by AWS including PII information such as customer first name, last name, email, phone. Partner is able to ingest this information into their CRM against the same record into their CRM | Pass
Business process : Partner is able to update an accepted opportunity (AWS Referral identified by OpportunityOwnership = "AWS Referral")
4 | Updatable Fields | As a Partner user I should be able to update the following fields by placing a file in a JSON format in the lead-inbound folder. I can send 1 or many of these fields along with the unique identifiers - apnCrmUniqueIdentifier and/or partnerCrmUniqueIdentifier Important pipeline fields highlighted in red { "version": "1", "spmsId": "397476", "leads": [ { "website": "www.netflix.com", "useCaseWorkload": "Content Delivery", "title": null, "streetAddress": "B-54, Tarang Co op housing society\r\n19 IP extension , patparganj", "status": "Qualified", "state": "Delhi", "segmentCompanySize": "aa", "projectDescription": "aa", "postalCode": "110092", "phone": "(206) 643-1476", "partnerCrmLeadId": "B", "levelofAWSUsage": "aa", "leadStatusReason": "aa", "leadSource": "3rd Party Event/Tradeshow", "leadOwnerName": "Abhisheikh Lahoti", "leadOwnerEmail": "lahotia@amazon.com", "leadAge": 0.0, "lastModifiedDate": "2020-02-20T21:36:24.000Z", "lastModifiedBy": "Abhisheikh Lahoti", "industry": "Internet Specific", "fullName": "Abhisheikh Lahoti Aditi Jitendra Bodha", "email": "aby10s@gmail.com", "createdDate": "2020-02-20T20:13:59.000Z", "createdBy": "Abhisheikh Lahoti", "country": "India", "company": "Amaze", "city": "Delhi", "campaignName": "AWS Campaign XYZ", "campaignMemberStatus": "Attended;Registered", "apnCrmUniqueIdentifier": "L128676" } ] } | The lead-inbound-processed-results folder will have the same file name as the input along with results appended to the end of the file name. The results file will highlight successful updates or errors if any. Note: If fields which are not updatable are shared, they will be ignored in the updates | Pass
Business process : Partner is able to consume updates from AWS Seller such as next steps (AWS Referral identified by OpportunityOwnership = "AWS Referral")
5 | Campaign Member Status | As a partner user I should check visibility of any updates to the campaign member status provided by AWS marketing team. Read the latest file from the lead-outbound folder. | As a partner user I should be able to view the campaign member status shared by AWS. Partner is able to ingest this information into their CRM against the same record into their CRM | Pass

## Launch Checklist
Checklist |  | Owner | Status
Kick Off | Overall alignment to implement CRM integration | AWS and Partner | Complete
| CRM integration documentation shared | AWS | Complete
Sandbox Set up and Testing | ARN Created by Partner | Partner | Complete
| S3 details shared by AWS | AWS | Complete
| Sandbox integration testing - Ability to read and update | Partner | Complete
| Field mapping exercise with source system | Partner | Complete
| Sandbox end to end testing from Partner CRM for business workflows | Partner | Complete
| Sandbox load testing | AWS/Partner | Complete
Compliance | Accept New ACE Terms and Conditions | Partner | In Progress
Production Set up | ARN Created by Partner (New account) | Partner | To begin
| S3 details shared by AWS | AWS | To begin
Go live | Production Go live (Soft launch) | AWS and Partner | To begin
| Share 1 live opportunity from AWS to test overall integration | AWS and Partner | To begin
Post Go live | Data backfill of Partner CRM identifier of existing Opps on both systems | Partner | To begin
| Evangelising new integration with partner's sales/ops teams | Partner | To begin
| Hypercare monitoring | AWS/Partner | To begin

## Integration Opportunity Fields
Field Name | Help text | Mandatory fIelds/Validations | Read/Update (All fields marked as update can be read as well) - After First Insert | Notes for each field while Opportunity is being created
useCase | End customer use case that the opportunity is solving for (E.g. Migration, Business applications) | Mandatory. Accepts only standard values | Update | Mandatory. Accepts only standard values
targetCloseDate | Expected launch date on the opportunity | Mandatory | Update | Mandatory. Accepts only today and future dates
subUseCase | End customer sub use case that the opportunity is solving for. These are further break ups of the use case | Accepts only Standard Values | Update | Optional. Accepts only standard values
streetAddress | Address of the end customer on the opportunity |  | Update | Optional
status | Field indicating whether AWS has approved or rejected the partner referral |  | Read Only | Not required while creating
state | State (part of the address) of the end customer on the opportunity | Accepts only Standard Values | Read Only | Mandatory when Country = United States (Check if bulk import has this experience.)
stage | Field indicating the opportunity lifecycle on the opportunity (E.g. Launched) | Mandatory. Accepts only standard values | Update | Not required while creating
publicReferenceUrl | URL of the customer public reference on the opportunity. This can be added once the opportunity is launched | Can be updated when Stage = Launched | Update | Not required while creating
publicReferenceTitle | Title of the customer public reference on the opportunity. This can be added once the opportunity is launched | Can be updated when Stage = Launched | Update | Not required while creating
projectDescription | Descriptive field articulating the details on the opportunity and the partners role on it | Mandatory | Read Only | Mandatory
primaryContactPhone | Phone number of the sales rep on the opportunity from the partner organization |  | Update | Optional
primaryContactLastName | Last Name of the sales rep on the opportunity from the partner organization |  | Update | Optional
primaryContactFirstName | First Name of the sales rep on the opportunity from the partner organization |  | Update | Optional
primaryContactEmail | Email of the sales rep on the opportunity from the partner organization |  | Update | Optional
postalCode | Postal Code (part of the address) of the end customer on the opportunity | Mandatory | Read Only | Mandatory
partnerProjectTitle | Title of the opportunity | Mandatory | Read Only | Mandatory
partnerPrimaryNeedFromAws | Partners primary need from AWS on the opportunity | Mandatory. Accepts only standard values | Update | Mandatory. Accepts only standard values
partnerPrimaryNeedFromAwsOther | If Partner Primary Need is Other then specify need |  |  | Mandatory if Partner Primary Need is specified as Other
partnerDeveloperManagerPhone | Phone number of the AWS Partner Development Manager on the Opportunity |  | Read Only | Not required while creating
partnerDeveloperManagerEmail | Email of the AWS Partner Development Manager on the Opportunity |  | Read Only | Not required while creating
partnerDeveloperManager | Name of the AWS Partner Development Manager on the Opportunity |  | Read Only | Not required while creating
partnerCrmUniqueIdentifier | Unique identifier of the opportunity in the Partner's CRM |  | Update | Mandatory. Unique across a partner. New opportunity is created if partnerCrmUniqueIdentifier is not available in PartnerCentral
opportunityOwnership | Field indicating the origination of the opportunity. Partner Referral will indicate it was submitted by Partner, AWS Referral will indicate it was originated by the seller | Accepts only Standard Values | Read Only | Not required while creating
opportunityOwnerName | Name of the owner of the opportunity in the Partner organization. This needs to be a Partner Central user | Mandatory | Update | Not required while creating
opportunityOwnerEmail | Email of the owner of the opportunity in the Partner organization. This needs to be a Partner Central user | Mandatory | Update | Mandatory. Partner Central user. If Not provided the opportunity is created with the Alliance lead on Partner Central as the owner.
nextStepHistory | History of the next steps on the opportunity |  | Read Only | Not required while creating
nextStep | Next steps on the opportunity. This is used to communicate to AWS the next action required |  | Update | Not required while creating
leadSource | Lead source on the opportunity |  | Read Only | Not required while creating
lastModifiedDate | Date-Time the opportunity was last modified |  | Read Only | Not required while creating
lastModifiedBy | Name of the person/entity that modified the opportunity |  | Read Only | Not required while creating
isThisForMarketplace | Yes/No field indicating if the opportunity is for AWS marketplace | Accepts only Standard Values | Update | Optional. Accepts only standard values
isThisAPublicReference | Yes/No field indicating if the opportunity can be referenced in public | Can be updated when Stage = Launched. Accepts only Standard Values | Update | Not required while creating
isNetNewBusinessForCompany | Yes/No field indicating if the opportunity is a net new business (customer) for the partner | Mandatory for ISV Accelerate Partners before if Stage = launched. Accepts only standard values | Update | Not required while creating
isMarketingDevelopmentFunded | Was this opportunity the result of a marketing development fund (MDF) funded activity? | Accepts only Standard Values | Update | Optional. Accepts only standard values
industryOther | Value indicating the Industry of the end customer on the opportunity (if the selection on the Industry field is other) |  | Update | Optional
industry | Industry of the end customer on the opportunity | Mandatory. Accepts only standard values | Update | Mandatory. Accepts only standard values
expectedMonthlyAwsRevenue | Expected monthly revenue on the opportunity. Please enter amount in USD. | Mandatory. Accepts only numbers | Update | Mandatory. Accepts only numbers greater than zero
deliveryModel | Indicate the most applicable deployment or consumption model for your solution or service | Mandatory. Accepts only standard values. This is a multi select. Multiple values need to sperated by semi colon | Update | Mandatory. Accepts only standard values. This is a multi select. Multiple values need to sperated by semi colon
customerWebsite | Website of the end customer on the opportunity | Mandatory | Read Only | Mandatory
customerTitle | Title of the end customer on the opportunity. (E.g. Mr., Mrs., Miss) |  | Update | Optional
customerPhone | Phone of the end customer on the opportunity |  | Update | Optional
customerLastName | Last Name of the end customer on the opportunity |  | Update | Optional
customerFirstName | First Name of the end customer on the opportunity |  | Update | Optional
customerEmail | Email of the end customer on the opportunity |  | Update | Optional
customerCompanyName | Name of the end customer company name on the opportunity | Mandatory | Read Only | Mandatory
createdDate | Date-Time the opportunity was created |  | Read Only | Not required while creating
createdBy | Name of the person/entity that created the opportunity |  | Read Only | Not required while creating
country | Country (part of the address) of the end customer on the opportunity | Mandatory. Accepts only standard values | Read Only | Mandatory. Accepts only standard values
contractVehicle | Contract Vehicle on the Opportunity. Used for Public Sector opportunities in the United States | Mandatory If country = "US" and Industry = "Government" or "Education" | Update | Mandatory If country = "US" and Industry = "Government" or "Education"
competitiveTracking | Identify other cloud providers who are potential competitors on the opportunity | Accepts only Standard Values | Update | Optional
competitiveTrackingOther | If Competitive tracking is "Other", specify which competitor |  |  | Mandatory IfcompetitiveTracking is Other
closedLostReason | Reason code for opportunity being Closed | Mandatory Only if Stage = Closed Lost | Update | Not required while creating
city | City (part of the address) of the end customer on the opportunity |  | Update | Optional
campaignName | AWS Campaign name on the opportunity to track campaign performance | Accepts only Standard Values | Update | Optional
aWSStage | Field indicating the opportunity lifecycle on the opportunity, as tracked by AWS (E.g. Launched) |  | Read Only | Not required while creating
aWSSalesRepName | Name of the AWS Sales Rep on the Opportunity. Primary point of contact from AWS on the opportunity |  | Read Only | Not required while creating
aWSSalesRepEmail | Email of the AWS Sales Rep on the Opportunity. Primary point of contact from AWS on the opportunity |  | Read Only | Not required while creating
aWSPartnerSuccessManagerName | Name of the Partner Success Manager on the Opportunity. Primary point of contact from AWS on the opportunity for Consulting partners |  | Read Only | Not required while creating
aWSPartnerSuccessManagerEmail | Email of the Partner Success Manager on the Opportunity. Primary point of contact from AWS on the opportunity for Consulting partners |  | Read Only | Not required while creating
aWSISVSuccessManagerName | Name of the ISV Success Manager on the Opportunity. Primary point of contact from AWS on the opportunity for Technology partners |  | Read Only | Not required while creating
aWSISVSuccessManagerEmail | Email of the ISV Success Manager on the Opportunity. Primary point of contact from AWS on the opportunity for Technology partners |  | Read Only | Not required while creating
awsFieldEngagement | Yes/No field indicating if the AWS Sales rep supported the partner on the opportunity (e.g. joint call or joint meeting with the customer) | Mandatory for ISV Accelerate Partners before if Stage = launched. Accepts only standard values | Update | Optional. Acceptes only standard values
aWSCloseDate | Expected launch date on the opportunity, as tracked by AWS |  | Read Only | Not required while creating
aWSAccountOwnerName | Name of the AWS account owner of the end customer on the Opportunity. |  | Read Only | Not required while creating
aWSAccountOwnerEmail | Email of the AWS account owner of the end customer on the Opportunity. |  | Read Only | Not required while creating
awsAccountId | 12 digit AWS Account number associated with the opportunity | Mandatory for Consulting Partners when if Stage ="Launched" | Update | Not required while creating
apnCrmUniqueIdentifier | Unique identifier of the opportunity in AWS APN system |  | Read Only | Not required while creating
additionalComments | Additional comments on the opportunity |  | Update | Optional
partnerAcceptanceStatus | Accepted/Rejected option for partners to accept or reject an opportunity shared by AWS. PII information on the opportunity is only available once partner accept the opportunity | Accepts only Standard Values | Update | Not required while creating
wWPSPDMEmail | Email of the relevant Partner Development manager on the opportunity |  | Read Only | Not required while creating
wWPSPDM | Name of the relevant Partner Development manager on the opportunity |  | Read Only | Not required while creating

## Standard Values on Opportunity
industry | country | State | partnerPrimaryNeedFromAws | competitiveTracking | useCase | subUseCase | campaignName | partnerAcceptanceStatus | stage | opportunityOwnership | isThisForResell | isThisForMarketplace | isThisAPublicReference | isNetNewBusinessForCompany | isMarketingDevelopmentFunded | isManagedServicesIncluded | deliveryModel | awsFieldEngagement
Industry Vertical (required) | Country (required) | State/Province | Partner Primary Need from AWS (required) | Competitive Tracking | Use Case (required) | Sub Use Case | Campaign Name | Partner Acceptance Status | Stage | opportunityOwnership | isThisForResell | isThisForMarketplace | isThisAPublicReference | isNetNewBusinessForCompany | isMarketingDevelopmentFunded | isManagedServicesIncluded | deliveryModel | awsFieldEngagement | Mapping of Use Case to Sub Use Case
Agriculture & Mining | United States | Ahmedabad | Architectural validation | Oracle Cloud | AI/Machine Learning | Content Creation & Processing | 3rd Party Event/ Trade Show | Accepted | Prospect | AWS Referral | Yes | Yes | Yes | Yes | Yes | Yes | SaaS or PaaS | Yes | Use Case (required) | Sub Use Case
Biotechnology | Afghanistan | Alabama | Business presentation | On-Prem | Big Data | Broadcast & OTT | APN Marketing Central | Rejected | Qualified | Partner Referral | No | No | No | No | No | No | BYOL or AMI | No | AI/Machine Learning | Computer Vision - Video Analysis, OCR, Medical Imaging, Face Detection, etc..
Business & Consumer Services | Aland Islands | Alaska | Competitive Information | Co-location | Business Applications | Content Management & Distribution | AWS DMS Program |  | Technical Validation | [7 empty] | Managed Services |  | AI/Machine Learning | Natural Language Understanding - Sentiment analysis, Topic modeling, Entity recognition, Language recognition, etc..
Business Serv. | Albania | Alberta | Pricing Assistance | Akamai | Cloud Management Tools & DevOps | High Performance Technical Computing (HPTC) | AWS Field Event |  | Business Validation | [7 empty] | Professional Services |  | AI/Machine Learning | Language Translation
Communications | Algeria | American Samoa | Technical consultation | AliCloud | Containers & Serverless | High Performance Business Computing (HPBC) | AWS Marketplace Campaign |  | Committed | [7 empty] | Resell |  | AI/Machine Learning | Text to speech, speech to text
Computer Hardware | American Samoa | Andaman & Nicobar | Total Cost of Ownership Evaluation | Google Cloud Platform | End User Computing | High Throughput Computing (HTC) | AWS Sponsorship |  | Launched | [7 empty] | Other |  | AI/Machine Learning | Recommendations
Computers & Electronics | Andorra | Andrapradesh | For Visibility - No Assistance Needed | IBM Softlayer | Energy | Connected Space | Database Ready Program |  | Closed Lost | [9 empty] | AI/Machine Learning | Forecasting - time series analysis, demand, etc..
Computer Software | Angola | Anhui | Deal support | Microsoft Azure | Financial Services | Connected Transport | Integrated Partner Campaign | [11 empty] | AI/Machine Learning | Personalization
Consumer Goods | Anguilla | Arizona | Other | Other- Cost Optimization | Healthcare & Life Sciences | Connected Commerce | ISV Workload Migration | [11 empty] | AI/Machine Learning | Conversational Interfaces
Consumer Related | Antarctica | Arkansas |  | No Competition | Hybrid application platform | Connected Operations | Migration Acceleration Program | [11 empty] | AI/Machine Learning | Fraud and Anomaly Detection
Education | Antigua And Barbuda | Arunachal Pradesh |  | *Other | Industrial Software | Connected Health | Partner Launch Initiative | [11 empty] | Big Data | Big data analytics & data science
Energy & Utilities | Argentina | Assam |  |  | IOT | Microsoft Apps | Partner Led Campaign | [11 empty] | Big Data | Business Intelligence & data visualization
Financial Services | Armenia | Australian Capital Territory |  |  | Media & High performance computing (HPC) | Oracle Production | Partner Led Event | [11 empty] | Big Data | Data integration & ETL
Gaming | Aruba | Bangalore |  |  | Migration | Oracle Non-Prod | Partner Opportunity Acceleration Funded | [11 empty] | Big Data | Data Warehouse
Government | Australia | Baroda |  |  | Networking | SAP Production | Partner Prospecting | [11 empty] | Big Data | Real-time Analytics
Government, Education & Public Services | Austria | Beijing |  |  | Security | SAP Non-Prod | Pipeline Builder | [11 empty] | Big Data | Data Lake
Healthcare | Azerbaijan | Bihar |  |  | Storage | Mainframe Modernization | The Next Smart | [11 empty] | Business Applications | Microsoft Apps
Healthcare, Pharmaceuticals and Biotech | Bahamas | British Columbia |  |  |  | Contact Center | VMware Cloud | [11 empty] | Business Applications | Oracle Production
Industrial/Energy | Bahrain | California |  |  |  | AWS Lambda | Well-Architected | [11 empty] | Business Applications | Oracle Non-Prod
Internet Specific | Bangladesh | Chattisgargh |  |  |  | Kubernetes | Windows RMP | [11 empty] | Business Applications | SAP Production
Life Sciences | Barbados | Chennai |  |  |  | OpenShift | Workspaces/AppStream Accelerator Program | [11 empty] | Business Applications | SAP Non-Prod
Manufacturing | Belarus | Chongqing |  |  |  | Database Migration | WWPS Bid Campaign | [11 empty] | Business Applications | Mainframe Modernization
Media, Entertainment & Leisure | Belgium | Cochin |  |  |  | Application Migration | WWPS NewBE | [11 empty] | Business Applications | Contact Center
Media & Entertainment | Belize | Colorado |  |  |  | Archive | [12 empty] | Cloud Management Tools & DevOps | Other
Medical/Health | Benin | Connecticut |  |  |  | Backup | [12 empty] | Cloud Management Tools & DevOps | Continuous Integration & Continuous Delivery (CICD)
Non-Profit Organization | Bermuda | Delaware |  |  |  | Primary Storage | [12 empty] | Cloud Management Tools & DevOps | Monitoring, logging and performance
Other | Bhutan | Delhi |  |  |  | Disaster Recovery | [12 empty] | Cloud Management Tools & DevOps | Infrastructure as code
Professional Services | Bolivia | Dist. of Columbia |  |  |  | Direct Connect | [12 empty] | Cloud Management Tools & DevOps | Productivity Applications
Public Services | Bonaire,Sint Eustatius and Saba | Federated States of Micronesia |  |  |  | Other | [12 empty] | Containers & Serverless | AWS Lambda
Real Estate & Construction | Bosnia and Herzegovina | Florida |  |  |  | Desktop & App Streaming | [12 empty] | Containers & Serverless | Kubernetes
Retail | Botswana | Fujian |  |  |  | Mobile Device and Application Management | [12 empty] | Containers & Serverless | OpenShift
Retail, Wholesale & Distribution | Bouvet Island | Gansu |  |  |  | End User Productivity Apps | [12 empty] | End User Computing | Desktop & App Streaming
Semiconductor/Electr | Brazil | Georgia |  |  |  | Big data analytics & data science | [12 empty] | End User Computing | Mobile Device and Application Management
Software & Internet | British Indian Ocean Territory | Goa |  |  |  | Business Intelligence & data visualization | [12 empty] | End User Computing | End User Productivity Apps
Telecommunications | Brunei Darussalam | Guam |  |  |  | Data integration & ETL | [12 empty] | Energy | Oil & Gas
Transportation & Logistics | Bulgaria | Guangdong |  |  |  | Data Warehouse | [12 empty] | Energy | Utilities
Travel & Hospitality | Burkina Faso | Guangxi |  |  |  | Real-time Analytics | [12 empty] | Financial Services | Insurance
Wholesale & Distribution | Burundi | Guizhou |  |  |  | Data Lake | [12 empty] | Financial Services | PCI
| Cambodia | Gujarat |  |  |  | Computer Vision - Video Analysis, OCR, Medical Imaging, Face Detection, etc.. | [12 empty] | Financial Services | Payment Processing
| Cameroon | Hainan |  |  |  | Natural Language Understanding - Sentiment analysis, Topic modeling, Entity recognition, Language recognition, etc.. | [12 empty] | Financial Services | Banking
| Canada | Haryana |  |  |  | Language Translation | [12 empty] | Financial Services | Capital Markets
| Cape Verde | Hawaii |  |  |  | Text to speech, speech to text | [12 empty] | Financial Services | Risk & Compliance
| Cayman Islands | Hebei |  |  |  | Recommendations | [12 empty] | Financial Services | Big Data/Grid
| Central African Republic | Heilongjiang |  |  |  | Forecasting - time series analysis, demand, etc.. | [12 empty] | Financial Services | Market Data & Financial Content
| Chad | Henan |  |  |  | Personalization | [12 empty] | Financial Services | Core Systems
| Chile | Himachal Pardesh |  |  |  | Conversational Interfaces | [12 empty] | Financial Services | Digital (AI/ML, Predicative Analytics)
| China | Hong Kong Island |  |  |  | Fraud and Anomaly Detection | [12 empty] | Healthcare & Life Sciences | Genomics
| Christmas Island | Hubei |  |  |  | Continuous Integration & Continuous Delivery (CICD) | [12 empty] | Healthcare & Life Sciences | HIPAA
| Cocos (Keeling) Islands | Hunan |  |  |  | Monitoring, logging and performance | [12 empty] | Healthcare & Life Sciences | HITRUST
| Colombia | Hyderabad |  |  |  | Infrastructure as code | [12 empty] | Healthcare & Life Sciences | GxP
| Comoros | Idaho |  |  |  | Productivity Applications | [12 empty] | Healthcare & Life Sciences | GDPR
| Congo | Illinois |  |  |  | Genomics | [12 empty] | Healthcare & Life Sciences | Biopharma
| Cook Islands | Indiana |  |  |  | HIPAA | [12 empty] | Healthcare & Life Sciences | Med device
| Costa Rica | Inner Mong |  |  |  | HITRUST | [12 empty] | Healthcare & Life Sciences | Payer
| Cote d'Ivoire | Iowa |  |  |  | GxP | [12 empty] | Healthcare & Life Sciences | Provider
| Croatia | Jiangsu |  |  |  | GDPR | [12 empty] | Industrial Software | Product Design and Simulation
| Cuba | Jiangxi |  |  |  | Biopharma | [12 empty] | Industrial Software | Electronic Design Automation
| Curacao | Jilin |  |  |  | Med device | [12 empty] | Industrial Software | Architecture Engineering and Construction
| Cyprus | Kansas |  |  |  | Payer | [12 empty] | Industrial Software | Other Engineering
| Czech Republic | Karnataka |  |  |  | Provider | [12 empty] | Industrial Software | Computer Aided Engineering
| Denmark | Kentucky |  |  |  | Insurance | [12 empty] | Industrial Software | Computer Aided Manufacturing
| Djibouti | Kerala |  |  |  | PCI | [12 empty] | Industrial Software | Product Lifecycle Management
| Dominica | Kolkata |  |  |  | Payment Processing | [12 empty] | Industrial Software | Production Planning
| Dominican Republic | Kowloon |  |  |  | Banking | [12 empty] | Industrial Software | Production – Automation
| Ecuador | Lantau Island |  |  |  | Capital Markets | [12 empty] | Industrial Software | Production – SCADA
| Egypt | Liaoning |  |  |  | Risk & Compliance | [12 empty] | Industrial Software | Production – MES
| El Salvador | Louisiana |  |  |  | Big Data/Grid | [12 empty] | Industrial Software | Industrial IoT
| Equatorial Guinea | Madhya Pradesh |  |  |  | Market Data & Financial Content | [12 empty] | Industrial Software | Industrial Asset Management
| Eritrea | Maharashtra |  |  |  | Core Systems | [12 empty] | Industrial Software | Production Logistics
| Estonia | Maine |  |  |  | Digital (AI/ML, Predicative Analytics) | [12 empty] | Industrial Software | Manufacturing Engineering System
| Ethiopia | Manipur |  |  |  | Product Design and Simulation | [12 empty] | IOT | Connected Space
| Falkland Islands (Malvinas) | Manitoba |  |  |  | Electronic Design Automation | [12 empty] | IOT | Connected Transport
| Faroe Islands | Marshall Islands |  |  |  | Architecture Engineering and Construction | [12 empty] | IOT | Connected Commerce
| Fiji | Maryland |  |  |  | Other Engineering | [12 empty] | IOT | Connected Operations
| Finland | Massachusetts |  |  |  | Computer Aided Engineering | [12 empty] | IOT | Connected Health
| France | Meghalaya |  |  |  | Computer Aided Manufacturing | [12 empty] | Media & High performance computing (HPC) | Content Creation & Processing
| French Guiana | Michigan |  |  |  | Product Lifecycle Management | [12 empty] | Media & High performance computing (HPC) | Broadcast & OTT
| French Polynesia | Minnesota |  |  |  | Production Planning | [12 empty] | Media & High performance computing (HPC) | Content Management & Distribution
| French Southern Territories | Mississippi |  |  |  | Production – Automation | [12 empty] | Media & High performance computing (HPC) | High Performance Technical Computing (HPTC)
| Gabon | Missouri |  |  |  | Production – SCADA | [12 empty] | Media & High performance computing (HPC) | High Performance Business Computing (HPBC)
| Gambia | Mizoram |  |  |  | Production – MES | [12 empty] | Media & High performance computing (HPC) | High Throughput Computing (HTC)
| Georgia | Montana |  |  |  | Industrial IoT | [12 empty] | Migration | Database Migration
| Germany | Mumbai |  |  |  | Industrial Asset Management | [12 empty] | Migration | Application Migration
| Ghana | Mysore |  |  |  | Production Logistics | [12 empty] | Networking | Direct Connect
| Gibraltar | Nagaland |  |  |  | Manufacturing Engineering System | [12 empty] | Networking | Other
| Great Britain | Navi Mumbai |  |  |  | Oil & Gas | [12 empty] | Storage | Archive
| Greece | Nebraska |  |  |  | Utilities | [12 empty] | Storage | Backup
| Greenland | NeiMongol | [16 empty] | Storage | Primary Storage
| Grenada | Nevada | [16 empty] | Storage | Disaster Recovery
| Guadeloupe | New Brunswick
| Guam | Newfoundland and Labrador
| Guatemala | New Hampshire
| Guernsey | New Jersey
| Guinea | New Mexico
| Guinea-Bissau | New South Wales
| Guyana | New Territories
| Haiti | New York
| Heard Island and McDonald Islands | Ningxia
| Holy See (Vatican City State) | North Carolina
| Honduras | North Dakota
| Hong Kong | Northern Mariana Islands
| Hungary | Northern Territory
| Iceland | Northwest Territories
| India | Nova Scotia
| Indonesia | Nunavut
| Iraq | Ohio
| Ireland | Oklahoma
| Isle of Man | Ontario
| Israel | Oregon
| Italy | Orrisa
| Jamaica | Palau
| Japan | Pennsylvania
| Jersey | Pondicherry
| Jordan | Prince Edward Island
| Kazakhstan | Puerto Rico
| Kenya | Pune
| Kiribati | Punjab
| Korea | Qinghai
| Kuwait | Quebec
| Kyrgyzstan | Queensland
| Lao People's Democratic Republic | Rajasthan
| Latvia | Rhode Island
| Lebanon | Saskatchewan
| Lesotho | Secunderabad
| Liberia | Shaanxi
| Libyan Arab Jamahiriya | Shandong
| Liechtenstein | Shanghai
| Lithuania | Shanxi
| Luxembourg | Sichuan
| MACAO | Singapore
| Macedonia, The former Yugoslav Republic Of | South Australia
| Madagascar | South Carolina
| Malawi | South Dakota
| Malaysia | Surat
| Maldives | Tamil Nadu
| Mali | Tasmania
| Malta | Tennessee
| Marshall Islands | Texas
| Martinique | Thiruvananthapuram
| Mauritania | Tianjin
| Mauritius | Tibet
| Mayotte | Tripura
| Mexico | Utah
| Micronesia, Federated States of | Uttar Pradesh
| Moldova, Republic of | Uttrakhand
| Monaco | Vermont
| Mongolia | Victoria
| Montenegro | Virginia
| Montserrat | Virgin Islands
| Morocco | Washington
| Mozambique | West Bangal
| Myanmar | Western Australia
| Namibia | West Virginia
| Nauru | Wisconsin
| Nepal | Wyoming
| Netherlands | Xinjiang
| Netherlands Antilles | Xizang
| New Caledonia | Yukon
| New Zealand | Yunnan
| Nicaragua | Zhejiang
| Niger | APO/AE
| Nigeria | AFO/FPO
| Niue | FPO, AP
Norfolk Island
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Palestinian Territory, Occupied
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Reunion
Romania
Russia
Rwanda
Saint Barthelemy
Saint Helena, Ascension and Tristan Da Cunha
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part )
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Serbia and Montenegro
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch Part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
Sudan
Suriname
Svalbard and Jan Mayen
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Taiwan
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom
United States Minor Outlying Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela
Viet Nam
VIRGIN ISLANDS, BRITISH
VIRGIN ISLANDS, U.S.
Wallis and Futuna
Western Sahara
Yemen
Zambia
Zimbabwe

## Integration Lead Fields
Field | Current Help Text | Mandatory fIelds/Validations | Read/Update
website | Website of the end customer on the lead |  | Update
useCaseWorkload | End customer use case that the lead is solving for (E.g. Migration, Business applications) |  | Update
title | Title of the end customer on the lead |  | Update
streetAddress | Address of the end customer on the lead |  | Update
status | Field indicating the status of the lead based on lifecycle (E.g. Open or Qualified or Closed) | Mandatory. Accepts only standard values | Update
state | State (part of the address) of the end customer on the lead |  | Update
segmentCompanySize | Company Size of the end customer on the lead |  | Update
projectDescription | Descriptive field articulating the customer need on the lead |  | Update
postalCode | Postal Code (part of the address) of the end customer on the lead |  | Update
phone | Phone number of the end customer on the lead |  | Update
partnerCrmLeadId | Unique identifier of the lead in the Partner's CRM |  | Update
Level of AWS Usage | End customer maturity on AWS |  | Read Only
leadStatusReason | Please provide details regarding your engagement and next steps with the lead. Do not disclose any information that is confidential, sensitive or that would be considered personal information of an individual. |  | Update
Lead Source | Lead source as maintained by AWS |  | Read Only
leadOwnerName | Name of the owner of the lead in the Partner organization. This needs to be a Partner Central user |  | Update
leadOwnerEmail | Email of the owner of the lead in the Partner organization. This needs to be a Partner Central user |  | Update
Lead Age | Age in days since the lead was created |  | Read Only
lastModifiedDate | Date-Time when the lead was last modified |  | Read Only
lastModifiedBy | Name of the person/entity that modified the lead |  | Read Only
industry | Industry of the end customer on the lead |  | Update
firstName | First name of the end customer on the lead | Visible only after Partner Accepts the lead | Update
lastName | Last name of the end customer on the lead | Visible only after Partner Accepts the lead | Update
email | Email of the end customer on the lead | Visible only after Partner Accepts the lead | Update
createdDate | Date-Time the lead was created |  | Read Only
createdBy | Name of the person/entity that created the lead |  | Read Only
country | Country (part of the address) of the end customer on the lead |  | Update
Company | Name of the end customer company name on the lead | Visible only after Partner Accepts the lead | Read Only
city | City (part of the address) of the end customer on the lead |  | Update
Campaign Name | AWS Campaign name that is associated with the lead generation |  | Read Only
CampaignMemberStatus | Level of engagement on the lead |  | Read Only
apnCrmUniqueIdentifier | Unique identifier of the lead in AWS APN system |  | Read Only
Current Lead Stage | Accepted/Rejected option for partners to accept or reject an opportunity shared by AWS. PII information on the opportunity is only available once partner accept the lead | Mandatory. Accepts only standard values | Update

## Standard Values on Lead
Industry Vertical (required) | Country (required) | State/Province | status | Use Case | Current Lead Stage
Agriculture & Mining | United States | Ahmedabad | Open | Big Data | Accepted
Biotechnology | Afghanistan | Alabama | Research | Content Delivery | Rejected
Business & Consumer Services | Aland Islands | Alaska | Disqualified | DR/Archive/Backup
Business Serv. | Albania | Alberta | Qualified | High Performance Computing (HPC)
Communications | Algeria | American Samoa |  | IOT
Computer Hardware | American Samoa | Andaman & Nicobar |  | Marketplace
Computers & Electronics | Andorra | Andrapradesh |  | Microsoft Apps
Computer Software | Angola | Anhui |  | Oracle/SAP/Enterprise Apps
Consumer Goods | Anguilla | Arizona |  | Other
Consumer Related | Antarctica | Arkansas |  | Web Application
Education | Antigua And Barbuda | Arunachal Pradesh
Energy & Utilities | Argentina | Assam
Financial Services | Armenia | Australian Capital Territory
Gaming | Aruba | Bangalore
Government | Australia | Baroda
Government, Education & Public Services | Austria | Beijing
Healthcare | Azerbaijan | Bihar
Healthcare, Pharmaceuticals and Biotech | Bahamas | British Columbia
Industrial/Energy | Bahrain | California
Internet Specific | Bangladesh | Chattisgargh
Life Sciences | Barbados | Chennai
Manufacturing | Belarus | Chongqing
Media, Entertainment & Leisure | Belgium | Cochin
Media & Entertainment | Belize | Colorado
Medical/Health | Benin | Connecticut
Non-Profit Organization | Bermuda | Delaware
Other | Bhutan | Delhi
Professional Services | Bolivia | Dist. of Columbia
Public Services | Bonaire,Sint Eustatius and Saba | Federated States of Micronesia
Real Estate & Construction | Bosnia and Herzegovina | Florida
Retail | Botswana | Fujian
Retail, Wholesale & Distribution | Bouvet Island | Gansu
Semiconductor/Electr | Brazil | Georgia
Software & Internet | British Indian Ocean Territory | Goa
Telecommunications | Brunei Darussalam | Guam
Transportation & Logistics | Bulgaria | Guangdong
Travel & Hospitality | Burkina Faso | Guangxi
Wholesale & Distribution | Burundi | Guizhou
| Cambodia | Gujarat
| Cameroon | Hainan
| Canada | Haryana
| Cape Verde | Hawaii
| Cayman Islands | Hebei
| Central African Republic | Heilongjiang
| Chad | Henan
| Chile | Himachal Pardesh
| China | Hong Kong Island
| Christmas Island | Hubei
| Cocos (Keeling) Islands | Hunan
| Colombia | Hyderabad
| Comoros | Idaho
| Congo | Illinois
| Cook Islands | Indiana
| Costa Rica | Inner Mong
| Cote d'Ivoire | Iowa
| Croatia | Jiangsu
| Cuba | Jiangxi
| Curacao | Jilin
| Cyprus | Kansas
| Czech Republic | Karnataka
| Denmark | Kentucky
| Djibouti | Kerala
| Dominica | Kolkata
| Dominican Republic | Kowloon
| Ecuador | Lantau Island
| Egypt | Liaoning
| El Salvador | Louisiana
| Equatorial Guinea | Madhya Pradesh
| Eritrea | Maharashtra
| Estonia | Maine
| Ethiopia | Manipur
| Falkland Islands (Malvinas) | Manitoba
| Faroe Islands | Marshall Islands
| Fiji | Maryland
| Finland | Massachusetts
| France | Meghalaya
| French Guiana | Michigan
| French Polynesia | Minnesota
| French Southern Territories | Mississippi
| Gabon | Missouri
| Gambia | Mizoram
| Georgia | Montana
| Germany | Mumbai
| Ghana | Mysore
| Gibraltar | Nagaland
| Great Britain | Navi Mumbai
| Greece | Nebraska
| Greenland | NeiMongol
| Grenada | Nevada
| Guadeloupe | New Brunswick
| Guam | Newfoundland and Labrador
| Guatemala | New Hampshire
| Guernsey | New Jersey
| Guinea | New Mexico
| Guinea-Bissau | New South Wales
| Guyana | New Territories
| Haiti | New York
| Heard Island and McDonald Islands | Ningxia
| Holy See (Vatican City State) | North Carolina
| Honduras | North Dakota
| Hong Kong | Northern Mariana Islands
| Hungary | Northern Territory
| Iceland | Northwest Territories
| India | Nova Scotia
| Indonesia | Nunavut
| Iraq | Ohio
| Ireland | Oklahoma
| Isle of Man | Ontario
| Israel | Oregon
| Italy | Orrisa
| Jamaica | Palau
| Japan | Pennsylvania
| Jersey | Pondicherry
| Jordan | Prince Edward Island
| Kazakhstan | Puerto Rico
| Kenya | Pune
| Kiribati | Punjab
| Korea | Qinghai
| Kuwait | Quebec
| Kyrgyzstan | Queensland
| Lao People's Democratic Republic | Rajasthan
| Latvia | Rhode Island
| Lebanon | Saskatchewan
| Lesotho | Secunderabad
| Liberia | Shaanxi
| Libyan Arab Jamahiriya | Shandong
| Liechtenstein | Shanghai
| Lithuania | Shanxi
| Luxembourg | Sichuan
| MACAO | Singapore
| Macedonia, The former Yugoslav Republic Of | South Australia
| Madagascar | South Carolina
| Malawi | South Dakota
| Malaysia | Surat
| Maldives | Tamil Nadu
| Mali | Tasmania
| Malta | Tennessee
| Marshall Islands | Texas
| Martinique | Thiruvananthapuram
| Mauritania | Tianjin
| Mauritius | Tibet
| Mayotte | Tripura
| Mexico | Utah
| Micronesia, Federated States of | Uttar Pradesh
| Moldova, Republic of | Uttrakhand
| Monaco | Vermont
| Mongolia | Victoria
| Montenegro | Virginia
| Montserrat | Virgin Islands
| Morocco | Washington
| Mozambique | West Bangal
| Myanmar | Western Australia
| Namibia | West Virginia
| Nauru | Wisconsin
| Nepal | Wyoming
| Netherlands | Xinjiang
| Netherlands Antilles | Xizang
| New Caledonia | Yukon
| New Zealand | Yunnan
| Nicaragua | Zhejiang
| Niger | APO/AE
| Nigeria | AFO/FPO
| Niue | FPO, AP
Norfolk Island
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Palestinian Territory, Occupied
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Reunion
Romania
Russia
Rwanda
Saint Barthelemy
Saint Helena, Ascension and Tristan Da Cunha
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part )
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Serbia and Montenegro
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch Part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
Sudan
Suriname
Svalbard and Jan Mayen
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Taiwan
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom
United States Minor Outlying Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela
Viet Nam
VIRGIN ISLANDS, BRITISH
VIRGIN ISLANDS, U.S.
Wallis and Futuna
Western Sahara
Yemen
Zambia
Zimbabwe

## UAT (hidden)
File
Test 5 | Curreny error

## Update Page (hidden)
Step # | Step by Step Instructions | Expected Results | Results | Pass/Fail | User Notes
Scenario 1:Update Page Layout (Opportunities)
1 | Login to UAT Sandbox. Navigate to an Account (Partner) who has accepted ACE Terms and Conditions - (E.g. - Slalom) |  |  | Pass
2 | Choose the Alliance lead for that Account (Partner) |  |  | Pass
3 | "Login to community as user". This will spoof you into a Partner Central account as the partner user you had selected |  |  | Pass
4 | Check for an opportunity with the Update Link | Step we are testing
5 | The new Opportunity will have the following Tabs 1. Detail 2. Customer 3. Contacts 4. Next Steps | Confirm all four tabs are visible |  | Pass
6 | The Partner Project Title is displayed as a header along with Stage and Status | Confirm if the display is accurate along with the following message :"Once the opportunity is submitted, you will not be able to update it until after it has been approved. Post Approval you are required to update the progress on the Opportunity till closure." |  | Pass
Scenario 2:Update Page Layout (Field View and Edit functionality)
1 | Login to UAT Sandbox. Navigate to an Account (Partner) who has accepted ACE Terms and Conditions - (E.g. - Slalom) |  |  | Pass
2 | Choose the Alliance lead for that Account (Partner) |  |  | Pass
3 | "Login to community as user". This will spoof you into a Partner Central account as the partner user you had selected |  |  | Pass
4 | Check for an opportunity with the Update Link |  |  | Pass
5 | The field mapping and editable logic is as below. Verify the same |  |  | Pass
| Field Label on Ux | Mandatory | Visible | Editable | Comments | Pass/Fail | User Notes
| Opportunity ID | Self Generated | Yes | No |  | Pass
| Partner Project Title | Mandatory at Edit and submission | Yes | No |  | Pass
| Status | Self Generated | Yes | No |  | Pass
| Customer Company Name | Mandatory at Edit and submission | Yes | No |  | Pass
| Street Address | Not Mandatory | Yes | Yes |  | Pass
| State/Province | Not Mandatory | Yes | Yes |  | Fail
| City | Not Mandatory | Yes | Yes |  | Pass
| Country | Mandatory at Edit and submission | Yes | No | Not Mandatory for AWS Referral | Pass | Doesn't have the asterisk for AWS Referral
| Postal Code | Mandatory at Edit and submission | Yes | No | Not Mandatory for AWS Referral | Pass | Doesn't have the asterisk for AWS Referral
| Customer Website | Mandatory at Edit and submission | Yes | No |  | Pass
| Industry Vertical | Mandatory at Edit and submission | Yes | No | Not Mandatory for AWS Referral | Pass | Doesn't have the asterisk for AWS Referral
| Contract Vehicle | Mandatory when Industry Vertical is Government and Country is United States | Yes | No |  | ? | Does this only show up when the industry vertical is Government?
| Project Description | Mandatory at Edit and submission | Yes | No |  | Pass
| Campaign Name | Not Mandatory | Yes | Yes |  | Pass
| Additional Comments | Not Mandatory | Yes | Yes |  | Pass
| Customer First Name | Not Mandatory | Yes | Yes |  | Pass
| Customer Last Name | Not Mandatory | Yes | Yes |  | Pass
| Customer Title | Not Mandatory | Yes | Yes |  | Pass
| Customer Phone | Not Mandatory | Yes | Yes |  | Pass
| Customer Email | Not Mandatory | Yes | Yes |  | Pass
| Stage | Mandatory at Edit | Yes | Yes |  | Pass
| Target Close Date | Mandatory at Edit and submission | Yes | Yes |  | Pass
| Closed Lost Reason | Not Mandatory | Yes | Yes |  | Fail
| Expected Monthly AWS Revenue | Mandatory at Edit and submission | Yes | Yes |  | Pass
| Is this for Resell? | Not Mandatory | Yes | Yes |  | Pass
| Competitive Tracking | Not Mandatory | Yes | Yes |  | Pass
| Other Competitors (Check if it is visible) | Not Mandatory | Yes | Yes |  | Fail
| Is this for Marketplace? | Not Mandatory | Yes | Yes |  | Pass
| Partner Primary Need from AWS | Mandatory at Edit and submission | Yes | Yes |  | Pass
| AWS Account ID | Not Mandatory | Yes | Yes |  | Pass
| Did an AWS Account Rep for this customer support you in this opportunity? | Not Mandatory | Yes | Yes |  | Pass
| Is this AWS Referred opportunity net new business for your company? | Not Mandatory | Yes | Yes |  | Pass
| Use Case | Mandatory at Edit and submission | Yes | Yes |  | Pass
| Sub Use Case | Not Mandatory | Yes | Yes |  | Pass
| Marketing Development Funded? | Not Mandatory | Yes | Yes |  | Pass
| Opportunity Include Managed Services? | Not Mandatory | Yes | Yes |  | Pass
Contacts Page
| AWS Sales Rep |  | Yes | No |  | Pass
| AWS Sales Rep Name | Not Mandatory | Yes | No |  | Pass
| AWS Sales Rep Email | Not Mandatory | Yes | No |  | Pass
| ACCOUNT MANAGER |  |  |  |  | Pass
| AWS Account Owner Name | Not Mandatory | Yes | No |  | Pass
| AWS Account Owner Email | Not Mandatory | Yes | No |  | Pass
| WWPS PARTNER DEVELOPMENT MANAGER |  |  |  |  | Pass
| WWPS PDM | Not Mandatory | Yes | No |  | Pass
| WWPS PDM EMAIL | Not Mandatory | Yes | No |  | Pass
Pass
| PARTNER DEVELOPMENT MANAGER |  | Yes | No |  | Pass
| Partner Developer Manager | Not Mandatory | Yes | No |  | Pass
| Partner Developer Manager Email | Not Mandatory | Yes | No |  | Pass
| Partner Developer Manager Phone | Not Mandatory | Yes | No |  | Pass
| PARTNER SALES CONTACT |  |  |  |  | Pass
| Partner Sales Rep Name | Not Mandatory | Yes | Yes |  | Fail
| Partner Sales Rep Email |  |  |  |  | Pass
| Partner Sales Rep Phone |  |  |  |  | Pass
| Next Steps | Not Mandatory | Yes | Yes |  | Pass | Add Next steps

## Debrief (hidden)
Test script | Scenario | Status | SIM No | Comments
Home Page | 1 | Pass
Home Page | 2 | Pass | https://issues.amazon.com/issues/APN-7628 | For a user without access to ACE - Open item - Phase 2 addition: 1) Change language ("Instead of Request Access button - "Email your alliance lead to provide access to APN Customer Engagements (ACE)")
Home Page | 3 | Pass
List Views | 1 | Pass |  | Should be a click back link (to go back to opp views) when theyre in import opp view (Incorporate in Bulk import functionality)
List Views | 2 | Pass
List Views | 3 | Pass
List Views | 4 | Pass | https://issues.amazon.com/issues/APN-7616
List Views | 5 | Pass |  | There's just a small lag before update appears (Adding a spinner)
List Views | 6 | Pass
Export Opportunity | 1 | Pass
Update Page | 1 | Pass
Update Page | 2 | Partial Pass with documented change requests | https://issues.amazon.com/issues/APN-7623 | Defects to be fixed 1. State/Province field is not editable - fail (Lahoti: To be fixed) New field to be added: 2. Adding Opportunity Ownership (To the detail section) Phase 2 change requests 1. Next Steps field is visible but no editable field. Is this only an option if the AM inputs next steps? (Lahoti : Add Next steps also on the detail page. Needs to be rescoped. This is not a launch blocker 2. On the next step page - are we able to reverse the view of the date from 2019/02/11 13:00 to 02/11/2019 and use 12 hours instead of 24? 3. Partner Sales Rep Name field is not editable - (Lahoti: This will hold true till we have the simple submission form going live. Partner sales Rep (or Primary Sales Contact) is mandatory while submission by a Partner and is a look up. When the new submission form will go live, this will be text fields and will be editable.) 4. Review/Update button on Partner Referred does the same thing Closed clarifications 1. Closed Lost Reason field is not editable - fail (Lahoti: This becomes editable when Stage = Closed Lost) 5. Country field does not have the mandatory asterisk mark (Lahoti: They are optional for a AWS Referral. Check Partner Referred and you can see the asterisk) 6. Postal Code field does not have the mandatory asterisk mark (Lahoti: They are optional for a AWS Referral. Check Partner Referred and you can see the asterisk) 7. Industry Vertical field does not have the mandatory asterisk mark (Lahoti: They are optional for a AWS Referral. Check Partner Referred and you can see the asterisk) 8. Contract Vehicle - Does this only show up when Industry Vertical is marked as Government? (Lahoti: Yes)
Regression Testing - Lead Referral | 1 | Pass
Regression Testing - Partner Referral | 2 | Pass
Regression Testing - AWS Referral | 3 | Partial Pass | https://issues.amazon.com/issues/APN-7629 | Change request 1. Partner Primary need from AWS or Use Case should not be mandatory to edit/update. (Not a launch blocker) 2. Opportunity Ownership is only visible on the column view but not in the actual opportunity. (Not a launch blocker) Phase 2 enhancement requests 1. Once the opportunity is marked as launched I cannot go back and make additional updates. The Partner should still be able to go in and mark updates even when the opportunity is marked as launched. (Lahoti : We need to hash out more requirement details here. Questions : What should the Partner be able to update. Which fields? Is it only next steps? Should we allow the Partner to take back the stage form Launched to Qualified for example? For Partner Referral, this is being overwritten by AWS SF. Should we allow Partners to override this? As part of Tier changes we will be making Customer References editable after an Opportunity is launched? Should we add more fields here? ) Closed clarifications 1. AWS Account ID isn't a required field to mark an op as launched but it should be. (Lahoti: We removed this condition in mid 2018, as it was causing updates from AWS SF to APN SF to fail as AWS does not have AWS Account ID mandatory) 2. I can't search OP ID in AWS SFDC - this should be a searchable field - (Lahoti: This is a request for GBO (Matt Racey))
Regression Testing - Bulk Update | 4 | Partial Pass with documented defects/clarifications | https://issues.amazon.com/issues/APN-7627 | Regression testing : Bulk update Defects 1. O97590 I was able to edit the stage from prospect to qualified without accepting the opportunity. Shouldn't this have failed? Also, why are unaccepted opportunities included in the download? Closed Clartifications 1. O97589 next step did not update, stage did. - Verified. This is working. Used Bulk update to update next steps at 1:47 PM. Was successful 2. General comment, I can't search by pressing the search button.. Verified. This is working. Search button has a lag but it is working.
Regression Testing - Bulk Import | 5 | Pass
Regression Testing - Localization | 6 | Refresh error on localization | https://issues.amazon.com/APN-7615 | Refresh error on choosing Partner Central language. This was changed

## Feedback (hidden)
Feedback
Field names - Rename AWS Field engagement
Update - Opp detail | PSM editable
Import template

## Field mapping to be tested (hidden)
AWS TO APN | [9 empty] | Permissions | [6 empty] | Validation and Sharing Rules
Destination Object on APN SF | Destination Field on APN | Source: Corresponding AWS Object | Source: Corresponding AWS Field Name | Flag for new Field to be created on AWS | Mandatory or not on AWS (Only for new fields, no change to existing fields) | New Field to be created on APN | Mandatory or not on APN. (Mentioned only for new field, no change to existing field) | Data Type | Comments | Visible on AWS UI (PAI) | Editable on AWS UI (PAI) | Visible on Share Communication Window | Visible to Partner | Editable by Partner | Tool Tips | Permissions | Validation Rules | Mandatory for sharing to APN | "Subsequent updates to fileds to flow over from AWS to APN"
APN Opportunity | Partner Account Name | PAI | Account Name | N | Already Mandatory in AWS | N |  | Lookup(Account) | To identify Partner and owner at APN end | Y |  | Y | [5 empty] | Mandatory | N
APN Opportunity | Partner SPMS ID | Partner Account | SPMS ID | N | Already Mandatory in AWS | N |  | Text(10) (External ID) (Unique Case Insensitive) |  |  |  | N | [5 empty] | Mandatory | N
APN Opportunity | Partner User Email Address | PAI | Partner User Email Address | Y | Not Mandatory | Y | Not Mandatory | Email |  |  |  | Y |  |  |  | Same as PAI | Should be an email | Not Mandatory | N
APN Opportunity | Affirmative Customer Consent Received | PAI | Affirmative Customer Consent Received | N | Not Mandatory. Mandatory only before sharing | Y | Mandatory for Opportunity Ownership = "AWS Referral" | Picklist |  |  |  | Y |  |  |  |  | Should be Y if Consent date added | Mandatory | Y
APN Opportunity | Customer Consent Received Date | PAI | Customer Consent Received Date | N | Not Mandatory. Mandatory only before sharing | Y | Mandatory for Opportunity Ownership = "AWS Referral" | Date |  |  |  | Y |  |  |  |  | Should not be in the future. Mandatory if Consent received set to Y | Mandatory | Y
APN Opportunity | Sharing Status | PAI | Sharing Status | Y | Mandatory. Defaults to Not shared through ACE | Y | Mandatory for Opportunity Ownership = "AWS Referral" | Picklist |  |  |  | N |  |  |  | Same as PAI |  | Mandatory | Y
APN Opportunity | Sharing Acknowledgement | PAI | Sharing Acknowledgement from APN | Y | Not Mandatory | N |  | Picklist | Sharing acknowledgemnet from APN post assignment to partner |  |  | N
APN Opportunity | Share Date | PAI | Share Date | Y | Not Mandatory. Mandatory only post sharing | Y | Mandatory for Opportunity Ownership = "AWS Referral" | Date Time | System captured date when acnowledgement received |  |  | N |  |  |  | Same as PAI | System captured date when acnowledgement received | Mandatory | Y
APN Opportunity | Customer Company Name (Opportunity Name) | Opportunity | Account Name | N | Already Mandatory in AWS | N |  | Text (255) |  |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | Customer First Name | Contact | Name | N | Apply validation | N |  | Text (80) |  |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | Customer Last Name | Contact |  | ? | Apply validation | N |  | Text (80) | How do you split this into First Name and Last Name? |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | Customer Title | Contact | Title | N | Apply validation | N |  | Text (80) |  |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | Customer Phone | Contact | Phone | N | Apply validation | N |  | Phone | If not mandatory at AWS end need to relax validation at APN end |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | Customer Email | Contact | Email | N | Apply validation | N |  | Email |  |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | AWS Account ID | Opportunity | AWS Account Number | N |  | N |  | Text (12) |  |  |  | Y | [5 empty] | Not Mandatory | N
APN Opportunity | Partner Project Title | Opportunity | Opportunity Name | N | Already Mandatory in AWS | N |  | Text (120) |  |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | Project Description/Business Need | PAI | Project Description to Share | Y | Not Mandatory. Mandatory only before sharing | N |  | Long Text Area (32000) |  |  |  | Y |  |  |  | Same as PAI |  | Mandatory | N
APN Opportunity | Next Steps | PAI | Next Steps for Partner | N | Not Mandatory. Mandatory only before sharing | N |  | Text (255) |  |  |  | Y |  |  |  | Same as PAI |  | Mandatory | Y
APN Opportunity | Expected Monthly AWS Revenue | Opportunity | Total Opportunity (Amount) | N | Apply validation | N |  | Currency(18, 0) |  |  |  | Y | [5 empty] | Mandatory | N
APN Opportunity | Industry Vertical | Account | Industry | N | Apply validation | N |  | Picklist | * Industry to be pulled from Account Name. Change management to new fields (Based on how AWS manages them) Pick List available in another tab of the excel |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | Industry Other | NA |  | ? |  | N |  | Text (255) | Tag as Other if there is no corresponding field |  |  | Y | [5 empty] | (required if Industry Vertical = Other) | N
APN Opportunity | Country | Account | Billing Country | N | Apply validation | N |  | Picklist | Check for mapping with country codes in APN. Pick List available in another tab of the excel |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | State/Province | Account | Billing State/Province | N |  | N |  | Picklist |  |  |  | Y | [5 empty] | required if country is Australia, Canada, China, India, United States | Y
APN Opportunity | Street Address | Account | Billing Street | N | Apply validation | N |  | Text (255) |  |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | City | Account | Billing City | N | Apply validation | N |  | Text (255) |  |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | Postal Code | Account | Billing Zip/Postal Code | N | Apply validation | N |  | Text (20) |  |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | Website | Account | Customer Website | N | Already Mandatory in AWS | N |  | URL (255) |  |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | Use Case | Opportunity | Use Cases | N | Apply validation | N |  | Picklist | Should we map this or not. Leave it blank as the pick list values differ? |  |  | Y | [5 empty] | Mandatory | N
APN Opportunity | Sub Use Case | NA |  | N |  | N |  | Picklist |  |  |  | N | [5 empty] | Not Mandatory | N
APN Opportunity | Target Close Date | Opportunity | Close Date | N | Already Mandatory in AWS | N |  | Date |  |  |  | Y | [5 empty] | Mandatory | N
APN Opportunity | AWS Sales Rep user Id | Opportunity | Opportunity Owner ID (18 digit) | N | Already Mandatory in AWS | N |  | SF ID (18 digit) |  |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | AWS Sales Rep First Name | Opportunity | Opportunity Owner Name | N | Already Mandatory in AWS | N |  | Text (255) |  |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | AWS Sales Rep Last Name | Opportunity | Opportunity Owner Last Name | N | Already Mandatory in AWS | N |  | Text (255) | Last Name to be derived from Full Name? |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | AWS Sales Rep Email | Opportunity | Opportunity Owner Email | N | Already Mandatory in AWS | N |  | Email |  |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | AWS Opportunity Id | Opportunity | Opportunity ID (18 digit) | N | Already Mandatory in AWS | N |  | SF ID (18 digit) |  |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | Partner Account Involved ID (required) | PAI | Partner Account Involved ID (18 digit) | N | Already Mandatory in AWS | N |  | SF ID (18 digit) |  |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | Partner Primary Need from AWS | NA | NA | N | Ignore check | N |  | Picklist | This is mandatory to create an APN opportunity. APN to handle change? |  |  | N | [5 empty] | Mandatory | N
APN Opportunity | Primary Sales Contact | NA | NA | N | Ignore check | N |  | Lookup (Contact) | This is mandatory to create an APN opportunity. APN to handle change? |  |  | N | [5 empty] | Mandatory | N
APN Opportunity | Is this for Marketplace? | NA | NA | N | Ignore check | N |  | Picklist | This is mandatory to create an APN opportunity. APN to handle change? |  |  | N | [5 empty] | Mandatory | N
APN Opportunity | AWS_ Close_Date | Opportunity | Close Date | N | Already Mandatory in AWS | Y | Not Mandatory | Date | Date from AWS |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | AWS AM_ user Id | Account | Account Owner ID | N | Already Mandatory in AWS | Y | Not Mandatory | SF ID (18 digit) |  |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | AWS_AM_First Name | Account | Account Owner Name | N | Already Mandatory in AWS | Y | Not Mandatory | Text (255) |  |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | AWS_AM_Email | Account | Account Owner Email | N | Already Mandatory in AWS | Y | Not Mandatory | Email |  |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | PSM Name | Account | PSM Name | N |  | Y | Not Mandatory | Text (255) |  |  |  | N | [5 empty] | Not Mandatory | Y
APN Opportunity | PSM Email | Account | ? | N |  | Y | Not Mandatory | Email |  |  |  | N | [5 empty] | Not Mandatory | Y
APN Opportunity | AWS Stage | Opportunity | Stage | N | Already Mandatory in AWS | Y | Not Mandatory | Picklist |  |  |  | Y | [5 empty] | Mandatory | Y
APN Opportunity | Primary Campaign Source | Opportunity | Primary Campaign Source | N |  | Y | Not Mandatory | Text (255) |  |  |  | Y | [5 empty] | Not Mandatory | Y
APN Opportunity | AWS Opportunity Record Type | Opportunity | AWS Opportunity Record Type | N | Already Mandatory in AWS | Y | Not Mandatory | Picklist |  |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | AWS Close Date | Opportunity | Close Date | N | Already Mandatory in AWS | Y | Not Mandatory | Date | Check Tier logic. Differentiate between partner revenue and AWS revenue |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | AWS Closed Lost Reason | Opportunity | Closed Lost Reason | N |  | Y | Not Mandatory | Picklist |  |  |  | N | [5 empty] | Not Mandatory | Y
APN Opportunity | Amount | Opportunity | Total Opportunity (Amount) | N | Apply validation | Y | Not Mandatory | Currency (18,0) | Check Tier logic. Differentiate between partner revenue and AWS revenue |  |  | N | [5 empty] | Not Mandatory | Y
APN Opportunity | Launched Stage Date | Opportunity | Launched Stage Date | N | Ignore check | Y | Not Mandatory | Date |  |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | Biz Unit | Opportunity | Biz Unit | N | Already Mandatory in AWS | Y | Not Mandatory | Picklist |  |  |  | N | [5 empty] | Mandatory | Y
APN Opportunity | Stage | Opportunity | Stage | n | Already Mandatory in AWS | n | [11 empty] | Mandatory | N
APN TO AWS | [9 empty] | Permissions | [6 empty] | Validation and Sharing Rules
Destination object on AWS Object | Destination AWS Field | Source: Corresponding APN Object | Source: Field Name on APN | Flag for new Field to be created on AWS | Mandatory or not on AWS (Only for new fields, no change to existing fields) | New Field to be created on APN | Mandatory or not on APN. (Mentioned only for new field, no change to existing field) | Data Type | Comments | Visible on AWS UI | Editable on AWS UI | Visible on Share Communication Window | Visible to Partner | Editable by Partner | Tool Tips | Permissions | Validation Rules | Mandatory for sharing to APN | "Subsequent updates to fileds to flow over from AWS to APN"
PAI | APN Partner Reported Status | APN Opportunity | Partner Acceptance Status | N | Not Mandatory. Mandatory post sharing | N |  | Picklist | Update picklist at APN end - Pending. Default to Pending | [6 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Partner Reported Stage | APN Opportunity | Stage | N | Not Mandatory. Mandatory post sharing | N |  | Picklist | [7 empty] | Same as PAI |  | Not Mandatory | Y
PAI | Next Step | APN Opportunity | Next Step | N | Not Mandatory. | N |  | Text (255) | [7 empty] | Same as PAI |  |  | Y
.
PAI | APN Opportunity Identifier | APN Opportunity | Opportunity Id | Y | Not Mandatory. Mandatory post sharing | N |  | Auto Number (External ID) |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Opportunity id | APN Opportunity | SF 18 Digit ID | Y | Not Mandatory. Mandatory post sharing | N |  | SF 18 digit ID |  | N | [5 empty] | Same as PAI
[8 empty] | . | [7 empty] | Same as PAI
PAI | APN AWS Account ID | APN Opportunity | AWS Account ID | Y | Not Mandatory. | N |  | Text (12) |  | Y | [7 empty] | Not Mandatory | Y
PAI | APN Target Launch Date | APN Opportunity | Close Date | Y | Not Mandatory. | N |  | Date |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Competitive Tracking | APN Opportunity | Competitive Tracking | Y | Not Mandatory. | N |  | Picklist |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Use Case | APN Opportunity | Use Case | Y | Not Mandatory. | N |  | Picklist |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Sub Use Case | APN Opportunity | Sub Use Case | Y | Not Mandatory. | N |  | Picklist |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Campaign Name | APN Opportunity | Campaign Name | Y | Not Mandatory. | N |  | Picklist |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN MDF Funded | APN Opportunity | Marketing Development Funded? | Y | Not Mandatory. | N |  | Picklist |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Closed Lost reason | APN Opportunity | Closed Lost Reason | Y | Not Mandatory. | N |  | Picklist |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Primary partner need from AWS | APN Opportunity | Partner Primary Need from AWS | Y | Not Mandatory. | N |  | Picklist |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Partner project budget | APN Opportunity | Expected Monthly AWS Revenue | Y | Not Mandatory. | N |  | Currency (18,0) |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Is the AWS Referral net new business for Partner? | APN Opportunity | Is This Net New Engagement With Customer | Y | Not Mandatory. | N |  | Picklist |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Did an AWS Account rep support Partner on this Opportunity? | APN Opportunity | AWS Field Engagement | Y | Not Mandatory. | N |  | Picklist |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Opportunity Title | APN Opportunity | Partner Project Title | Y | Not Mandatory. | N |  | Text (60) | [7 empty] | Same as PAI |  |  | Y
PAI | APN other relevant issues | APN Opportunity | ? | Y | Not Mandatory. | N |  |  | Check existing mapping | [9 empty] | Y
PAI | APN is this for resell? | APN Opportunity | Is this for Resell? | Y | Not Mandatory. | N |  | Picklist | [7 empty] | Same as PAI |  |  | Y
PAI | APN Other competitors | APN Opportunity | Other Competitors | Y | Not Mandatory. | N |  | Text (255) | [7 empty] | Same as PAI |  |  | Y
PAI | APN Partner Probability (%) | APN Opportunity | Probability (%) | Y | Not Mandatory. | N |  | Percent (3,0) | [7 empty] | Same as PAI |  |  | Y
PAI | APN Contract Vehicle | APN Opportunity | Contract Vehicle | Y | Not Mandatory. | N |  | Text (255) | [7 empty] | Same as PAI |  |  | Y
PAI | APN End customer GEO | APN Opportunity | ? | Y | Not Mandatory. | N |  | Text (255) | [7 empty] | Same as PAI |  |  | Y
[8 empty] | . | [10 empty] | Y
PAI | APN Accepted Time | APN Opportunity | Partner Accepted Time | Y | Not Mandatory. | Y | Not Mandatory | Date Time | Auto capture when Partner accepts an opportunity | n | [5 empty] | Same as PAI |  |  | Y
PAI | APN Rejected Time | APN Opportunity | Partner Rejected Time | Y | Not Mandatory. | Y | Not Mandatory | Date Time | Auto capture when Partner rejects an opportunity | n | [5 empty] | Same as PAI |  |  | Y
PAI | APN Launched Stage Time | APN Opportunity | Partner Launched Stage Time | Y | Not Mandatory. | Y | Not Mandatory | Date Time | Auto capture when Partner marks stage as Launched on opportunity | n | [5 empty] | Same as PAI | Should be updated when stage moved out from launch to blank |  | Y
PAI | APN Partner Last Modified By | APN Opportunity | Last Modified By | Y | Not Mandatory. | N |  | Lookup (user) |  | y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Partner Last Modified Date | APN Opportunity | Last Modified Date/By | N | Not Mandatory. | N |  | Date Time |  | y | [5 empty] | Same as PAI |  | Not Mandatory | Y
[8 empty] | . | [10 empty] | Y
PAI | APN Partner Sales Contact Name | APN Opportunity | Partner Sales Rep Name | Y | Not Mandatory. | N |  | Text (255) | Contact Information | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Partner Sales Contact Email | APN Opportunity | Partner Sales Rep Email | Y | Not Mandatory. | N |  | Email |  | Y | [5 empty] | Same as PAI |  |  | Y
PAI | APN Partner Sales Contact Phone | APN Opportunity | Partner Sales Rep Phone | Y | Not Mandatory. | N |  | Phone |  | Y | [5 empty] | Same as PAI |  |  | Y
PAI | APN Alliance Lead Name | Account | Alliance Lead Full Name | Y | Not Mandatory. | N |  | Text (255) |  | Y | [5 empty] | Same as PAI |  |  | Y
PAI | APN Alliance Lead Email | Account | AL Email | Y | Not Mandatory. | N |  | Email |  | Y | [5 empty] | Same as PAI |  | Not Mandatory | Y
PAI | APN Alliance Lead Phone | Account | AL Phone | Y | Not Mandatory. | N |  | Phone |  | Y | [5 empty] | Same as PAI |  |  | Y
PAI | APN Opportunity Owner Name | APN Opportunity | Opportunity Owner | Y | Not Mandatory. | N |  | Text (255) - Lookup from (User) |  | N | [5 empty] | Same as PAI |  |  | Y
PAI | APN Opportunity Owner Email | APN Opportunity | Opportunity Owner Email | Y | Not Mandatory. | N |  | Email |  | N | [5 empty] | Same as PAI |  |  | Y
PAI | APN Opportunity Owner Phone | APN Opportunity | Opportunity Owner Phone | Y | Not Mandatory. | N |  | Phone (Lookup form (User)) |  | N | [5 empty] | Same as PAI |  |  | Y
PAI | Rejected Reason Code | APN Opportunity | Rejected Reason Code | Y | Not Mandatory. | Y | Not Mandatory. | Picklist | [7 empty] | Same as PAI |  | Not Mandatory | Y

## Sheet2 (hidden)
Pass/Fail
Pass
Fail

## Defects - Open (hidden)
SIM NO | SIM Title | Status

## Defects - Resolved (hidden)
SIM NO | SIM Title | Status

## Backlog (hidden)
SIM NO | SIM Title | Status