## Checklist
Category | Task# | Task List | Owner | Environment |  | Details |  | Comments/FAQs | Information needed by APN Team
|  |  |  | Sand-box (Dev/Beta) | Production | Sand-Box (Dev/Beta) | Production
On-boarding | O1 | AWS Account creation | Partner | X | X |  |  | A) How to create a AWS account? Follow the steps mentioned in the below link. https://aws.amazon.com/es/premiumsupport/knowledge-center/create-and-activate-aws-account/
| O2 | IAM User creation Recommended IAM user format: APN-ACE-<PartnerName>-AccessUser-beta | Partner | X | X | Partner to provide Dev/Beta IAM user ARN to APN team. | Partner to provide Production IAM user ARN to APN team when ready for prod deployment. | B) How to create a IAM user? Follow the steps in the below link. https://docs.aws.amazon.com/IAM/latest/UserGuide/id_users_create.html
| O3 | S3 buckets and folders creation by APN team | APN Team | X | X
| O4 | Grant Access to Partner IAM user | APN team | X | X | APN team will grant the access and confirm | APN team will grant the access and confirm
| O5 | Share the policy with partners | APN team | x | x | APN team will provide the bucket policy which includes bucket and KMS key name for beta | APN team will provide the bucket policy which includes bucket and KMS key name for production | 1. How do we get key details? Yes, Key name is already included in the policy. 2. How often we rotate the keys? 90 days. Key name is same, no need to update partners for any keys rotation.
| O6 | Attach policy to the above IAM user to allow connection to the APN S3 buckets. Sample Policy is provided in the Integration doc. | Partner | X | X
Read Operation ( Read the data from APN by partner) | R1 | Authentication to APN S3 | APN team | X | X
| R2 | Uploading file to APN S3 folders (lead-outbound, opportunity-outbound) | APN team | X | X |  |  | 3. What is the format of the leads and opportunities? The format for leads and opportunities read and update operations is provided as attachments (Sample_Lead_Outbound.json and Sample_Opportunity_Outbound.json) in the email. 4. What is the frequency of file uploads by APN? Either 15 or 30 minutes depending on what we agree with the partner.
| R3 | Pull the file from APN S3 folders ( opportunity-outbound and lead-outbound) | Partner | X | X
| R4 | Delete the file from APN S3 folders ( opportunity-outbound and lead-outbound) after pulling | Partner | X | X |  |  | 5. When the files have to be deleted? Delete only after successful processing at their end. If partially updated, you can tag the files as well. 6. Incase if we delete by mistake, where can I find the original files? The files will be available in the opportunity-outbound-archive and lead-outbound-archive)
| R5 | Process the file into Partner systems | Partner |  |  |  |  | 7. What needs to be done when there is any data file issues? Raise a ticket with APN Support.
Update/Create Operation (Provide new data or updates on existing data to APN by Partner) | U1 | Authentication to APN S3 | Partner |  |  |  |  | 8. How to autheticate S3 from SFDC? Sample code file (Authentication.cls) to authenticate the S3 from SFDC is provided as an attachment to the email
| U2 | Upload the file to the APN S3 folders (lead-inbound, opportunity-inbound) | Partner | X | X |  |  | 9. What is the format for leads and opportunities? The format for leads and opportunities is provided as attachments (Sample_Lead_Outbound.json and Sample_Opportunity_Outbound.json) in the email. The structure is same for both read and update operations. Incase of update operation, we will ignore the fileds which are read only fields mentioned in the Data Fields Definitions file Shared by us. We make updates in our system for the fields which are marked as updatable. 10. How to upload the file from SFDC to S3? Sample code file (Sample_AceOutboundBatch.cls) for uploading the data file from SFDC is provided as an attachment to the email 11. Is there any file naming convention? Each file name need to be unique. The recommended file name is 'Partner provided file name+timestamp.json'
| U3 | Process the inbound file and provide results into lead-inbound-processed-results and opportunity-inbound-processed-results. | APN | X | X |  |  | 12. What is the structure of the results? Sample files for the results (success, error and partial) provided for reference. 13. What is the naming convention of the results? Partner given file name_results.json 14. What happens if partner gives duplicate file? We will not process the file and file will be moved to archive folder. 15. What is the inbound file size? 1MB 16. What happens if files with extension such as .pdf, .docx other than .json uploaded? We will reject the files and generate *._error.json file with the reason details.
| U4 | Archive the files to the folders (lead-inbound-archive, opportunity-inbound-archive) | APN | X | X
| U5 | Pull the results file for reconciliation/errors and delete after successful pull. | Partner | X | X |  |  | 17. What needs to be done when there is any data file issues? a) If the data needs to be corrected at partner CRM system, send us the revised file after correcting the data. b) If any clarifications required for the data, reach out to PDMs. c) If any technical support required, reach out to APN support by raising a ticket. 18. How long the results file will be available ? Partners can delete the files after successful pull. 19. Incase if we need to find the results file after deletion, where can we find? You can find the results files in the lead-inbound-results-archive and opportunity-inbound-results-archive 20. If there is any failure in processing the file by APN, how do we get to know? APN has alarms which will autocreate sev2 tickets to track the processing errors at APN. We will review, resolve and communicate to partners. 21. If there is no files coming to or going from APN? i.e. inactivity at partner end or at APN end. To be discussed. no activity? If the partner not picked up the file, what to do? Flexibility? region perspective...